## E2NS
[7 empty] | January 25 |  |  | February 25 |  |  |  | March 25 |  |  |  |  | April 25 |  |  |  | May 25 |  |  |  | June 25
|  |  | Status | Target Completion | Total |  | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23
01.10 | Already Executed -Progress since April 2024 |  | DONE | 3 | 382722.5666 | Cyrille | 382722.5666 | 0 | 215478.1479 | 0 | 190356.6632 | 0 | 326928.0084 | 0 | 218438.1754 | 0 | 196557.2103 | 0 | 251338.0863 | 0 | 346719.1777 | 0 | 246887.6264 | 0 | 254065.762 | 0 | 153519.4504
[6 empty] | Umut | January 25 3: 382722.5666; January 25 5: 276819.103; February 25 7: 213029.1773; February 25 9: 296122.2767; March 25 11: 228268.595; March 25 13: 251212.7861; April 25 15: 259167.1207; April 25 17: 327821.7086; May 25 19: 259881.712; May 25 21: 249522.6143; June 25 23: 38443.6579
02.10 | E2N | [5 empty] | January 25 3: 0; January 25 5: -61340.9551; February 25 7: -22672.514; February 25 9: 30805.7316; March 25 11: -9830.4195; March 25 13: -54655.5758; April 25 15: -7829.0344; April 25 17: 18897.4692; May 25 19: -12994.0856; May 25 21: 4543.1477; June 25 23: 115075.7926
02.11 | FT07/FT08/FT11/FT15 East | _E2N |  | 11 | 14255.0117
02.12 | FT15: E2N (NW) / E2S (ESW) / NTA60 (Terminal C. Tray) | _E2N |  | 9 | 51428.0084
02.13 | Lochfenster-E2N&E2S | _E2N |  | 21 | 22479.6293
02.14 | Türen E2N | _E2N |  | 23 | 25685.4898
02.15 | Main Entrance Canopy_E2N Novotel | _E2N |  | 21 | 1306.1346
02.16 | Lamellenfassade FT18_E2N | _E2N |  | 15 | 11045.642
02.17 | Stabgeländer E2N&E2S + NTA053 | _E2N |  | 21 | 21663.4046
02.18 | Attikaabdeckungen_E2N&E2S | _E2N |  | 21 | 14593.6002
02.19 | Acoustic Panel_MOS | _E2N |  | 9 | 95000
02.20 | Acoustic Panels Subframe_MOS | _E2N |  | 11 | 114000
02.21 | Acoustic Panels Installation _ Cat Walk (NTA047) | _E2N |  | 15 | 151496.0602
02.22 | Final Façade Cleaning E2N&E2S | _E2N |  | 23 | 7819.5452
0
03.10 | E2N -Additional Works |  |  |  | 0
03.11 | Sheet WT01 (NTA050) / Sheet OG3 North (NTA051) | _E2N |  | 11 | 36983.1637
567755.6897
|  |  | Status | Target Completion | Total
04.10 | E2S
04.11 | PR-Fassade - FT02/FT03/FT10/FT14 | _E2S |  | 21 | 35683.8429
04.12 | PR-Fassade - FT05/FT06/FT09 / Interkom Glass (NTA063) | _E2S |  | 15 | 55655.9175
04.13 | Lochfenster-WT04 | _E2S |  | 13 | 47907.3853
04.14 | Lochfenster - WT01.5 / WT01.6 / WT01.7 | _E2S |  | 15 | 33140.4667
04.15 | Türen E2S | _E2S |  | 21 | 22620.5829
04.16 | Lamellenfassade FT18_E2S | _E2S |  | 19 | 20452.5731
04.17 | Main Entrance Canopy_E2S Pullmann | _E2S |  | 19 | 30526.5055
04.18 | Alu Cladding Shafts_FT16 | _E2S |  | 17 | 57000
04.19 | Aluminium Soffit_FT17 | _E2S |  | 21 | 70643.5675
0
05.10 | E2S- Additional Works |  |  |  | 0
05.11 | Justifications NTA: 048,049,54,55,56,57,62 |  | DONE | 5 | 161453.5479
05.12 | 3.OG Attika Rectification (NTA054) | _E2S |  | 7 | 21377.7882
05.13 | NTA: 058 (FT14 Spandrel) / 059 (E2S West_Louvers) 052 (Attika) / 065 (Cty Water Tap) | _E2S |  | 17 | 78344.1777
05.14 | FT16 Additional Steel Structure (NTA061) | _E2S |  | 19 | 195908.5478
830714.9031
Final Milestone
| Due on completion of all final snags & submission of documentation |  |  | 23 | 73603.7154
73603.7154
|  |  | Status | Target Completion | Total
02.10 |  | D1D2
01.11 |  | Interior Façade Defects removal _D2-6 Floors |  | 7 | 47500
01.12 |  | Interior Façade Defects removal _D2-6 Floors |  | 9 | 47500
01.13 |  | Interior Façade Defects removal _D1-6 Floors |  | 9 | 47500
01.14 |  | Interior Façade Defects removal _D1-6 Floors |  | 11 | 47500
01.15 |  | Exterior Facade Defects removal |  | 17 | 84550
01.16 |  | Glass replacement |  | 17 | 79325
01.17 |  | Staircases: Material on site, NTA040 included |  | 9 | 85500
01.18 |  | Staircases: Completion , NTA040 included |  | 13 | 47500
01.19 |  | Doors Defects |  | 21 | 65075
01.20 |  | Electrical bird deterrence system_D2-12 Floors |  | 13 | 101149.825
01.21 |  | Electrical bird deterrence system_D1-12Floors |  | 7 | 101149.825
01.22 |  | Final Façade Cleaning |  | 17 | 47500
801749.65
02.10 |  | D1D2 - Additional Works
02.11 |  | Staircase Design Revision |  | 5 | 20273.95
02.12 |  | 4.OG Additional Vent _MOS |  | 7 | 14535
02.13 |  | 4.OG Additional Vent _Installation (NTA041) |  | 11 | 5700
02.14 |  | Justifications NTA: 042, 043, 044, 045, 046 | DONE | 5 | 33750.65
02.15 |  | Logo Anchorage Installation with Abseilers |  | 7 | 5794.05
80053.65
Final Milestone
| Due on completion of all final snags & submission of documentation |  |  | 23 | 46410.7

## D1D2
|  |  | Status | Target Completion | Total
02.10 |  | D1D2
01.11 |  | Interior Façade Defects removal _D2-12 Floors |  | 9 | 95000
01.12 |  | Interior Façade Defects removal _D1-12 Floors |  | 11 | 95000
01.13 |  | Exterior Facade Defects removal |  | 17 | 84550
01.14 |  | Glass replacement |  | 17 | 79325
01.15 |  | Staircases: Material on site, NTA040 included |  | 9 | 85500
01.16 |  | Staircases: Completion , NTA040 included |  | 13 | 47500
01.17 |  | Doors Defects |  | 21 | 65075
01.18 |  | Electrical bird deterrence system_D2-12 Floors |  | 13 | 101149.825
01.19 |  | Electrical bird deterrence system_D1-12Floors |  | 7 | 101149.825
01.20 |  | Final Façade Cleaning |  | 17 | 47500
801749.65
02.10 |  | D1D2 - Additional Works
02.11 |  | Staircase Design Revision |  | 5 | 20273.95
02.12 |  | 4.OG Additional Vent _MOS |  | 7 | 14535
02.13 |  | 4.OG Additional Vent _Installation (NTA041) |  | 11 | 5700
02.14 |  | Justifications NTA: 042, 043, 044, 045, 046 | DONE | 5 | 33750.65
02.15 |  | Logo Anchorage Installation with Abseilers |  | 7 | 5794.05
80053.65
Final Milestone
| Due on completion of all final snags & submission of documentation |  |  | KW23 | 46410.7
46410.7

## Claude Log
Turn # | Date | User Request | Action Taken | Details | Outcome
1 | 2026-02-06 | Highlight rows A:F on E2NS sheet by payment week (column E). Use a gradient color scheme from nearest (week 3) to farthest (week 23), with each week getting a distinct color. | Applied background colors to 46 rows across columns A:F based on their payment week value. | 11 unique weeks (3,5,7,9,11,13,15,17,19,21,23) mapped to a green→yellow→orange→red gradient. Week 3=#AAEDAA (green/nearest), Week 13=#EDEDAA (yellow/middle), Week 23=#EDAAAA (red/farthest). Used Office.js to apply fill colors efficiently. | All 46 data rows in E2NS!A:F are now color-coded by payment week. Green = nearest, red = farthest.
2 | 2026-02-06 | Create a new sheet listing all activities grouped by payment week, with a separate table for each week (CW 3 through CW 23) for follow-up tracking. | Created 'Weekly Follow-Up' sheet with 11 separate tables, one per calendar week. | Each table has: week header (darker shade), column headers (Code, Activity Description, Area, Status, Week, Total €), data rows, and a SUM subtotal row. Same green→red gradient colors as E2NS sheet. 46 activities across CW 3,5,7,9,11,13,15,17,19,21,23. Fixed 4 subtotal rows that were overwritten during parallel writes. | New sheet 'Weekly Follow-Up' complete with all 11 weekly tables and working subtotals. All activities from E2NS (E2N, E2S, D1D2 sections) are included.
3 | 2026-02-06 | Duplicate Weekly Follow-Up and add detailed sub-activities from the uploaded MYA Proposal Excel file. Expand grouped items (e.g. 'Justifications NTA: 048,049,54...') into individual NTA/FT lines with codes and descriptions. | Created 'Weekly Detailed Follow-Up' sheet with 46 parent activities + 68 sub-detail rows from MYA Proposal file. | Parsed uploaded file '260206_Copy of 260114_E2NS_D1D2_MYA Rest to Spend_Sample.xlsx' (sheets: Cyrille Sample, MYA Proposal). Extracted activity codes (col E) and descriptions (col F). Mapped 30 parent activities to their sub-items (NTAs, FTs, WTs). Sub-rows shown in italic gray with ↳ prefix, indented under bold parent rows. Parent rows have week-color background; sub-rows are white. Subtotals SUM only parent rows. | New sheet 'Weekly Detailed Follow-Up' complete with 160 rows. All 11 weekly tables expanded with sub-activity details from MYA Proposal.

## Weekly Follow-Up
Activities by Payment Week - Follow-Up Tracker
CW 3
Code | Activity Description | Area | Status | Week | Total (€)
1.1 | Already Executed - Progress since April 2024 |  | DONE | 3 | 382722.57
|  |  |  | Subtotal: | 382722.57
CW 5
Code | Activity Description | Area | Status | Week | Total (€)
5.11 | Justifications NTA: 048,049,54,55,56,57,62 | _E2S | DONE | 5 | 161453.55
2.11 | Staircase Design Revision | D1D2 |  | 5 | 20273.95
2.14 | Justifications NTA: 042, 043, 044, 045, 046 | D1D2 | DONE | 5 | 33750.65
|  |  |  | Subtotal: | 215478.15
CW 7
5.12 | 3.OG Attika Rectification (NTA054) | _E2S |  | 7 | 21377.79
1.11 | Interior Façade Defects removal _D2-6 Floors | D1D2 |  | 7 | 47500
1.21 | Electrical bird deterrence system_D1-12Floors | D1D2 |  | 7 | 101149.83
2.12 | 4.OG Additional Vent _MOS | D1D2 |  | 7 | 14535
2.15 | Logo Anchorage Installation with Abseilers | D1D2 |  | 7 | 5794.05
|  |  |  | Subtotal: | 190356.67
Code | Activity Description | Area | Status | Week | Total (€)
2.12 | FT15: E2N (NW) / E2S (ESW) / NTA60 (Terminal C. Tray) | _E2N |  | 9 | 51428.01
2.19 | Acoustic Panel_MOS | _E2N |  | 9 | 95000
1.12 | Interior Façade Defects removal _D2-6 Floors | D1D2 |  | 9 | 47500
1.13 | Interior Façade Defects removal _D1-6 Floors | D1D2 |  | 9 | 47500
1.17 | Staircases: Material on site, NTA040 included | D1D2 |  | 9 | 85500
|  |  |  | Subtotal: | 326928.01
CW 11
2.11 | FT07/FT08/FT11/FT15 East | _E2N |  | 11 | 14255.01
2.2 | Acoustic Panels Subframe_MOS | _E2N |  | 11 | 114000
3.11 | Sheet WT01 (NTA050) / Sheet OG3 North (NTA051) | _E2N |  | 11 | 36983.16
1.14 | Interior Façade Defects removal _D1-6 Floors | D1D2 |  | 11 | 47500
2.13 | 4.OG Additional Vent _Installation (NTA041) | D1D2 |  | 11 | 5700
|  |  |  | Subtotal: | 218438.17
CW 13
Code | Activity Description | Area | Status | Week | Total (€)
4.13 | Lochfenster-WT04 | _E2S |  | 13 | 47907.39
1.18 | Staircases: Completion, NTA040 included | D1D2 |  | 13 | 47500
1.2 | Electrical bird deterrence system_D2-12 Floors | D1D2 |  | 13 | 101149.83
|  |  |  | Subtotal: | 196557.22
CW 15
2.16 | Lamellenfassade FT18_E2N | _E2N |  | 15 | 11045.64
2.21 | Acoustic Panels Installation / Cat Walk (NTA047) | _E2N |  | 15 | 151496.06
4.12 | PR-Fassade - FT05/FT06/FT09 / Interkom Glass (NTA063) | _E2S |  | 15 | 55655.92
4.14 | Lochfenster - WT01.5 / WT01.6 / WT01.7 | _E2S |  | 15 | 33140.47
|  |  |  | Subtotal: | 251338.09
CW 17
4.18 | Alu Cladding Shafts_FT16 | _E2S |  | 17 | 57000
5.13 | NTA: 058 (FT14 Spandrel) / 059 (E2S West_Louvers) / 052 (Attika) / 065 (Cty Water Tap) | _E2S |  | 17 | 78344.18
1.15 | Exterior Facade Defects removal | D1D2 |  | 17 | 84550
1.16 | Glass replacement | D1D2 |  | 17 | 79325
1.22 | Final Façade Cleaning | D1D2 |  | 17 | 47500
|  |  |  | Subtotal: | 346719.18
CW 19
4.16 | Lamellenfassade FT18_E2S | _E2S |  | 19 | 20452.57
4.17 | Main Entrance Canopy_E2S Pullmann | _E2S |  | 19 | 30526.51
5.14 | FT16 Additional Steel Structure (NTA061) | _E2S |  | 19 | 195908.55
|  |  |  | Subtotal: | 246887.63
Code | Activity Description | Area | Status | Week | Total (€)
2.13 | Lochfenster-E2N&E2S | _E2N |  | 21 | 22479.63
2.15 | Main Entrance Canopy_E2N Novotel | _E2N |  | 21 | 1306.13
2.17 | Stabgeländer E2N&E2S + NTA053 | _E2N |  | 21 | 21663.4
2.18 | Attikaabdeckungen_E2N&E2S | _E2N |  | 21 | 14593.6
4.11 | PR-Fassade - FT02/FT03/FT10/FT14 | _E2S |  | 21 | 35683.84
4.15 | Türen E2S | _E2S |  | 21 | 22620.58
4.19 | Aluminium Soffit_FT17 | _E2S |  | 21 | 70643.57
1.19 | Doors Defects | D1D2 |  | 21 | 65075
|  |  |  | Subtotal: | 254065.75
CW 23
Code | Activity Description | Area | Status | Week | Total (€)
2.14 | Türen E2N | _E2N |  | 23 | 25685.49
2.22 | Final Façade Cleaning E2N&E2S | _E2N |  | 23 | 7819.55
| Final Milestone - E2NS: Due on completion of all final snags & submission of documentation |  |  | 23 | 73603.72
| Final Milestone - D1D2: Due on completion of all final snags & submission of documentation |  |  | 23 | 46410.7
|  |  |  | Subtotal: | 153519.46

## Weekly Detailed Follow-Up
Activities by Payment Week - Detailed Follow-Up Tracker
CW 3
Code | Activity Description | Area | Status | Week | Total (€)
01.10 | Already Executed - Progress since April 2024 |  | DONE | 3 | 382722.57
|  |  |  | Subtotal: | 382722.57
CW 5
Code | Activity Description | Area | Status | Week | Total (€)
05.11 | Justifications NTA: 048,049,54,55,56,57,62 | _E2S | DONE | 5 | 161453.55
NTA048 | ↳ Attika Removal + Substructure on East
NTA049 | ↳ Steel Construction for Masonry on E2S West
NTA054 | ↳ 3.OG Attika Rectification
NTA055 | ↳ 3.OG Balustrade + Machinery
NTA056 | ↳ FT18 Late + Tough Installation
NTA057 | ↳ Design Revision of Glass Balustrade
NTA062 | ↳ FT12 Canopy Drainage Pipe
02.11 | Staircase Design Revision | D1D2 |  | 5 | 20273.95
NTA040 | ↳ Staircase Design Revision
02.14 | Justifications NTA: 042, 043, 044, 045, 046 | D1D2 | DONE | 5 | 33750.65
NTA042 | ↳ 1.OG Perforated Sheets
NTA043 | ↳ Additional Gal. Sheet on Roof
NTA044 | ↳ Boon Edam Commissioning
NTA045 | ↳ Pesca Water Ingress x 4 Times
NTA046 | ↳ Logo Anchorage Installation with Abseilers
|  |  |  | Subtotal: | 215478.15
CW 7
Code | Activity Description | Area | Status | Week | Total (€)
05.12 | 3.OG Attika Rectification (NTA054) | _E2S |  | 7 | 21377.79
NTA054 | ↳ 3.OG Attika Rectification
01.11 | Interior Façade Defects removal _D2-6 Floors | D1D2 |  | 7 | 47500
3.1.1 | ↳ D2-12 Floors (Interior Defects)
01.21 | Electrical bird deterrence system_D1-12Floors | D1D2 |  | 7 | 101149.83
3.6.2 | ↳ D1-12 Floors (Bird Deterrence)
02.12 | 4.OG Additional Vent _MOS | D1D2 |  | 7 | 14535
NTA041 | ↳ 4.OG Additional Vent
02.15 | Logo Anchorage Installation with Abseilers | D1D2 |  | 7 | 5794.05
NTA046 | ↳ Logo Anchorage Installation with Abseilers
|  |  |  | Subtotal: | 190356.67
CW 9
Code | Activity Description | Area | Status | Week | Total (€)
02.12 | FT15: E2N (NW) / E2S (ESW) / NTA60 (Terminal C. Tray) | _E2N |  | 9 | 51428.01
1.1.5 | ↳ FT15/West+North
2.1.7 | ↳ FT15 / OST
2.1.8 | ↳ FT15 / South
2.1.9 | ↳ FT15 / West
NTA060 | ↳ Terminal Cable Canals
02.19 | Acoustic Panel_MOS | _E2N |  | 9 | 95000
01.12 | Interior Façade Defects removal _D2-6 Floors | D1D2 |  | 9 | 47500
3.1.1 | ↳ D2-12 Floors (Interior Defects)
01.13 | Interior Façade Defects removal _D1-6 Floors | D1D2 |  | 9 | 47500
3.1.2 | ↳ D1-12 Floors (Interior Defects)
01.17 | Staircases: Material on site, NTA040 included | D1D2 |  | 9 | 85500
3.4.1 | ↳ Al. Cladding - Anchorage + Substructure ¦ MOS
3.4.3 | ↳ Balustrade ¦ MOS
NTA040 | ↳ Staircase Design Revision
|  |  |  | Subtotal: | 326928.01
CW 11
Code | Activity Description | Area | Status | Week | Total (€)
02.11 | FT07/FT08/FT11/FT15 East | _E2N |  | 11 | 14255.01
1.1.1 | ↳ FT07
1.1.2 | ↳ FT08
1.1.3 | ↳ FT11
1.1.4 | ↳ FT15/OST
1.1.5 | ↳ FT15/West+North
02.20 | Acoustic Panels Subframe_MOS | _E2N |  | 11 | 114000
03.11 | Sheet WT01 (NTA050) / Sheet OG3 North (NTA051) | _E2N |  | 11 | 36983.16
NTA050 | ↳ Bottom Sheet Reinforcement on WT01
NTA051 | ↳ Cutting Bottom Sheet on 3.OG North Face
01.14 | Interior Façade Defects removal _D1-6 Floors | D1D2 |  | 11 | 47500
3.1.2 | ↳ D1-12 Floors (Interior Defects)
02.13 | 4.OG Additional Vent _Installation (NTA041) | D1D2 |  | 11 | 5700
NTA041 | ↳ 4.OG Additional Vent
|  |  |  | Subtotal: | 218438.17
CW 13
Code | Activity Description | Area | Status | Week | Total (€)
04.13 | Lochfenster-WT04 | _E2S |  | 13 | 47907.39
2.3.1 | ↳ WT04
01.18 | Staircases: Completion, NTA040 included | D1D2 |  | 13 | 47500
3.4.2 | ↳ Al. Cladding ¦ Installation
3.4.4 | ↳ Balustrade ¦ Installation
NTA040 | ↳ Staircase Design Revision
01.20 | Electrical bird deterrence system_D2-12 Floors | D1D2 |  | 13 | 101149.83
3.6.1 | ↳ D2-12 Floors (Bird Deterrence)
|  |  |  | Subtotal: | 196557.22
CW 15
Code | Activity Description | Area | Status | Week | Total (€)
02.16 | Lamellenfassade FT18_E2N | _E2N |  | 15 | 11045.64
02.21 | Acoustic Panels Installation / Cat Walk (NTA047) | _E2N |  | 15 | 151496.06
1.9.3 | ↳ Installation Completed
NTA047 | ↳ Cat Walk on Acoustic Roof
04.12 | PR-Fassade - FT05/FT06/FT09 / Interkom Glass (NTA063) | _E2S |  | 15 | 55655.92
2.1.2 | ↳ FT05
2.1.3 | ↳ FT06
2.1.4 | ↳ FT09
NTA063 | ↳ Interkom Glasses
04.14 | Lochfenster - WT01.5 / WT01.6 / WT01.7 | _E2S |  | 15 | 33140.47
2.3.2 | ↳ WT01.5+WT01.7
2.3.3 | ↳ WT01.6
|  |  |  | Subtotal: | 251338.09
CW 17
Code | Activity Description | Area | Status | Week | Total (€)
04.18 | Alu Cladding Shafts_FT16 | _E2S |  | 17 | 57000
2.8.1 | ↳ FT16
05.13 | NTA: 058 (FT14 Spandrel) / 059 (E2S West_Louvers) / 052 (Attika) / 065 (Cty Water Tap) | _E2S |  | 17 | 78344.18
NTA058 | ↳ FT14 Additional Spandrel Panel
NTA059 | ↳ E2S West Vent behind louvers
NTA052 | ↳ 1141 Partial Additional Attika
NTA065 | ↳ E2N Courtyard Water Tap
01.15 | Exterior Facade Defects removal | D1D2 |  | 17 | 84550
01.16 | Glass replacement | D1D2 |  | 17 | 79325
01.22 | Final Façade Cleaning | D1D2 |  | 17 | 47500
|  |  |  | Subtotal: | 346719.18
CW 19
Code | Activity Description | Area | Status | Week | Total (€)
04.16 | Lamellenfassade FT18_E2S | _E2S |  | 19 | 20452.57
04.17 | Main Entrance Canopy_E2S Pullmann | _E2S |  | 19 | 30526.51
05.14 | FT16 Additional Steel Structure (NTA061) | _E2S |  | 19 | 195908.55
NTA061 | ↳ FT16 Additional Steel Structure
|  |  |  | Subtotal: | 246887.63
CW 21
Code | Activity Description | Area | Status | Week | Total (€)
02.13 | Lochfenster-E2N&E2S | _E2N |  | 21 | 22479.63
02.15 | Main Entrance Canopy_E2N Novotel | _E2N |  | 21 | 1306.13
02.17 | Stabgeländer E2N&E2S + NTA053 | _E2N |  | 21 | 21663.4
1.7.0 | ↳ Edelstahl-Stabgeländer E2N
2.6.0 | ↳ Glas- und Stabgeländer E2S
NTA053 | ↳ Additional Steel Balustrade
02.18 | Attikaabdeckungen_E2N&E2S | _E2N |  | 21 | 14593.6
1.8.0 | ↳ Attikaabdeckungen_E2N
2.9.0 | ↳ Attikaabdeckungen
04.11 | PR-Fassade - FT02/FT03/FT10/FT14 | _E2S |  | 21 | 35683.84
2.1.10 | ↳ FT02
2.1.1 | ↳ FT03
2.1.5 | ↳ FT10
2.1.6 | ↳ FT14
04.15 | Türen E2S | _E2S |  | 21 | 22620.58
04.19 | Aluminium Soffit_FT17 | _E2S |  | 21 | 70643.57
2.8.2 | ↳ FT17
01.19 | Doors Defects | D1D2 |  | 21 | 65075
|  |  |  | Subtotal: | 254065.75
CW 23
Code | Activity Description | Area | Status | Week | Total (€)
02.14 | Türen E2N | _E2N |  | 23 | 25685.49
02.22 | Final Façade Cleaning E2N&E2S | _E2N |  | 23 | 7819.55
1.10.0 | ↳ Final Façade Cleaning
2.10.0 | ↳ Final Façade Cleaning
| Final Milestone - E2NS: Due on completion of all final snags & submission of documentation |  |  | 23 | 73603.72
| Final Milestone - D1D2: Due on completion of all final snags & submission of documentation |  |  | 23 | 46410.7
|  |  |  | Subtotal: | 153519.46