## Summary
|  | Week Number | 2
General Summary
|  | Group | Total Manday | Total Manday x Progress | Progress | Total Manday x Progress Should be | Progress Should be
| A | Rectafications | 2349 | 214.8354 | 9.146% | 298 | 12.69%
| B | Contract | 1342 | 80.4534 | 5.995% | 62 | 4.62%
| C | NTA | 522 | 65.6037 | 12.57% | 45 | 8.621%
|  |  | 4213 | 360.8925 | 8.566% | 405 | 9.613%
|  | Group | Total Manday | Total Manday x Progress | Progress | Total Manday x Progress Should be | Progress Should be
|  | E2N | 1610 | 204.1889 | 12.68% | 294 | 18.26%
1 | A | Rectafications | 1222 | 164.1889 | 13.44% | 262 | 21.44%
1 | B | Contract | 124 | 40 | 32.26% | 32 | 25.81%
1 | C | NTA | 264 | 0 | 0% | 0 | 0%
|  | E2S Exterior | 1155 | 156.7035 | 13.57% | 105 | 9.091%
2 | A | Rectafications | 687 | 50.6464 | 7.372% | 30 | 4.367%
2 | B | Contract | 336 | 40.4534 | 12.04% | 30 | 8.929%
2 | C | NTA | 132 | 65.6037 | 49.7% | 45 | 34.09%
|  | E2S Courtyard | 936 | 0 | 0% | 6 | 0.641%
3 | A | Rectafications | 120 | 0 | 0% | 6 | 5%
3 | B | Contract | 714 | 0 | 0% | 0 | 0%
3 | C | NTA | 102 | 0 | 0% | 0 | 0%
|  | E2S Interior | 512 | 0 | 0% | 0 | 0%
4 | A | Rectafications | 320 | 0 | 0% | 0 | 0%
4 | B | Contract | 168 | 0 | 0% | 0 | 0%
4 | C | NTA | 24 | 0 | 0% | 0 | 0%
|  |  | 4213 | 360.8925 | 8.566% | 405 | 9.613%

## E2NS Terminplan
[24 empty] | 2025-10-01 | November 25 | [6 empty] | December 25 | [6 empty] | December 25 | [6 empty] | December 25 | [6 empty] | December 25 | [6 empty] | January 26 | [6 empty] | January 26 | [6 empty] | January 26 | [6 empty] | January 26 | [6 empty] | January 26 | [6 empty] | February 26 | [6 empty] | February 26 | [6 empty] | February 26 | [6 empty] | February 26 | [6 empty] | March 26 | [6 empty] | March 26 | [6 empty] | March 26 | [6 empty] | March 26 | [6 empty] | April 26 | [6 empty] | April 26 | [6 empty] | April 26 | [6 empty] | April 26 | [6 empty] | May 26 | [6 empty] | May 26 | [6 empty] | May 26 | [6 empty] | May 26 | [6 empty] | May 26 | [6 empty] | June 26 | [6 empty] | June 26 | [6 empty] | June 26 | [6 empty] | June 26 | [6 empty] | July 26 | [6 empty] | July 26 | [6 empty] | July 26 | [6 empty] | July 26 | [6 empty] | August 26 | [6 empty] | August 26 | [6 empty] | August 26 | [6 empty] | August 26 | [6 empty] | August 26 | [6 empty] | September 26 | [6 empty] | September 26 | [6 empty] | September 26 | [6 empty] | September 26 | [6 empty] | October 26 | [6 empty] | October 26 | [6 empty] | October 26 | [6 empty] | October 26 | [6 empty] | October 26 | [6 empty] | November 26 | [6 empty] | November 26 | [6 empty] | November 26
[16 empty] | E2NS | [8 empty] | 48 | [6 empty] | 49 | [6 empty] | 50 | [6 empty] | 51 | [6 empty] | 52 | [6 empty] | 1 | [6 empty] | 2 | [6 empty] | 3 | [6 empty] | 4 | [6 empty] | 5 | [6 empty] | 6 | [6 empty] | 7 | [6 empty] | 8 | [6 empty] | 9 | [6 empty] | 10 | [6 empty] | 11 | [6 empty] | 12 | [6 empty] | 13 | [6 empty] | 14 | [6 empty] | 15 | [6 empty] | 16 | [6 empty] | 17 | [6 empty] | 18 | [6 empty] | 19 | [6 empty] | 20 | [6 empty] | 21 | [6 empty] | 22 | [6 empty] | 23 | [6 empty] | 24 | [6 empty] | 25 | [6 empty] | 26 | [6 empty] | 27 | [6 empty] | 28 | [6 empty] | 29 | [6 empty] | 30 | [6 empty] | 31 | [6 empty] | 32 | [6 empty] | 33 | [6 empty] | 34 | [6 empty] | 35 | [6 empty] | 36 | [6 empty] | 37 | [6 empty] | 38 | [6 empty] | 39 | [6 empty] | 40 | [6 empty] | 41 | [6 empty] | 42 | [6 empty] | 43 | [6 empty] | 44 | [6 empty] | 45 | [6 empty] | 46 | [6 empty] | 47
[25 empty] | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 129 | 130 | 131 | 132 | 133 | 134 | 135 | 136 | 137 | 138 | 139 | 140 | 141 | 142 | 143 | 144 | 145 | 146 | 147 | 148 | 149 |  | 151 | 152 | 153 | 154 | 155 | 156 | 157 | 158 | 159 | 160 | 161 | 162 | 163 | 164 | 165 | 166 | 167 | 168 | 169 | 170 | 171 | 172 | 173 | 174 | 175 | 176 | 177 | 178 | 179 | 180 | 181 | 182 | 183 | 184 | 185 | 186 | 187 | 188 | 189 | 190 | 191 | 192 | 193 | 194 | 195 | 196 | 197 | 198 | 199 | 200 | 201 | 202 | 203 | 204 | 205 | 206 | 207 | 208 | 209 | 210 | 211 | 212 | 213 | 214 | 215 | 216 | 217 | 218 | 219 | 220 | 221 | 222 | 223 | 224 | 225 | 226 | 227 | 228 | 229 | 230 | 231 | 232 | 233 | 234 | 235 | 236 | 237 | 238 | 239 | 240 | 241 | 242 | 243 | 244 | 245 | 246 | 247 | 248 | 249 | 250 | 251 | 252 | 253 | 254 | 255 | 256 | 257 | 258 | 259 | 260 | 261 | 262 | 263 | 264 | 265 | 266 | 267 | 268 | 269 | 270 | 271 | 272 | 273 | 274 | 275 | 276 | 277 | 278 | 279 | 280 | 281 | 282 | 283 | 284 | 285 | 286 | 287 | 288 | 289 | 290 | 291 | 292 | 293 | 294 | 295 | 296 | 297 | 298 | 299 | 300 | 301 | 302 | 303 | 304 | 305 | 306 | 307 | 308 | 309 | 310 | 311 | 312 | 313 | 314 | 315 | 316 | 317 | 318 | 319 | 320 | 321 | 322 | 323 | 324 | 325 | 326 | 327 | 328 | 329 | 330 | 331 | 332 | 333 | 334 | 335 | 336 | 337 | 338 | 339 | 340 | 341 | 342 | 343 | 344 | 345 | 346 | 347 | 348 | 349 | 350 | 351 | 352 | 353 | 354 | 355 | 356 | 357 | 358 | 359 | 360 | 361 | 362 | 363 | 364 | 365 | 366 | 367 | 368 | 369 | 370 | 371 | 372 | 373 | 374 | 375 | 376 | 377 | 378 | 379 | 380 | 381 | 382 | 383 | 384 | 385 | 386 | 387 | 388 | 389 | 390 | 391 | 392 | 393 | 394 | 395 | 396 | 397 | 398 | 399 | 400 | 401 | 402 | 403 | 404
[25 empty] | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun
[25 empty] | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 49 | 49 | 49 | 49 | 49 | 49 | 49 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 43 | 43 | 43 | 43 | 43 | 43 | 43 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 47 | 47 | 47 | 47 | 47 | 47 | 47
x | time axis 2025-11-24 to 2026-11-22
|  |  | Pos. | Aufgabe/Tätigkeit | Presequities | Responsible | Group | QTY | Done | Rem. | Manpower | Duration | Total Manday |  |  | Beginn [Datum] | Ende nach [AT] | Ende [Datum] | Status |  | KW2 Progress | Cumulative Progress =<KW2 |  | Anmerkungen | bar: 2025-11-30; 2025-12-05 to 2025-12-07; 2025-12-14; 2025-12-19 to 2025-12-21
[13 empty] | 4169 | [5 empty] | 8.848% |  | 2026-01-11 |  |  |  | 2025-11-24: 15; 2025-11-25: 15; 2025-11-26: 15; 2025-11-27: 15; 2025-11-28: 15; 2025-11-29: 15; 2025-11-30: 0; 2025-12-01: 19; 2025-12-02: 19; 2025-12-03: 19; 2025-12-04: 19; 2025-12-05: 19; 2025-12-06: 19; 2025-12-07: 0; 2025-12-08: 23; 2025-12-09: 23; 2025-12-10: 23; 2025-12-11: 27; 2025-12-12: 27; 2025-12-13: 23; 2025-12-14: 0; 2025-12-15: 23; 2025-12-16: 23; 2025-12-17: 23; 2025-12-18: 23; 2025-12-19: 23; 2025-12-20: 2; 2025-12-21: 0; 2025-12-22: 2; 2025-12-23: 2; 2025-12-24: 2; 2025-12-25: 2; 2025-12-26: 2; 2025-12-27: 2; 2025-12-28: 0; 2025-12-29: 2; 2025-12-30: 2; 2025-12-31: 2; 2026-01-01: 2; 2026-01-02: 2; 2026-01-03: 2; 2026-01-04: 0; 2026-01-05: 2; 2026-01-06: 2; 2026-01-07: 2; 2026-01-08: 2; 2026-01-09: 2; 2026-01-10: 2; 2026-01-11: 0; 2026-01-12: 29; 2026-01-13: 29; 2026-01-14: 29; 2026-01-15: 29; 2026-01-16: 29; 2026-01-17: 29; 2026-01-18: 0; 2026-01-19: 32; 2026-01-20: 32; 2026-01-21: 32; 2026-01-22: 32; 2026-01-23: 32; 2026-01-24: 32; 2026-01-25: 0; 2026-01-26: 34; 2026-01-27: 34; 2026-01-28: 34; 2026-01-29: 34; 2026-01-30: 34; 2026-01-31: 34; 2026-02-01: 0; 2026-02-02: 39; 2026-02-03: 39; 2026-02-04: 39; 2026-02-05: 35; 2026-02-06: 35; 2026-02-07: 35; 2026-02-08: 0; 2026-02-09: 36; 2026-02-10: 36; 2026-02-11: 36; 2026-02-12: 36; 2026-02-13: 36; 2026-02-14: 36; 2026-02-15: 0; 2026-02-16: 37; 2026-02-17: 37; 2026-02-18: 37; 2026-02-19: 37; 2026-02-20: 37; 2026-02-21: 37; 2026-02-22: 0; 2026-02-23: 37; 2026-02-24: 37; 2026-02-25: 37; 2026-02-26: 37; 2026-02-27: 37; 2026-02-28: 37; 2026-03-01: 0; 2026-03-02: 40; 2026-03-03: 40; 2026-03-04: 40; 2026-03-05: 40; 2026-03-06: 40; 2026-03-07: 40; 2026-03-08: 0; 2026-03-09: 46; 2026-03-10: 46; 2026-03-11: 46; 2026-03-12: 46; 2026-03-13: 46; 2026-03-14: 46; 2026-03-15: 0; 2026-03-16: 44; 2026-03-17: 44; 2026-03-18: 44; 2026-03-19: 44; 2026-03-20: 44; 2026-03-21: 44; 2026-03-22: 0; 2026-03-23: 46; 2026-03-24: 46; 2026-03-25: 46; 2026-03-26: 46; 2026-03-27: 46; 2026-03-28: 46; 2026-03-29: 0; 2026-03-30: 41; 2026-03-31: 41; 2026-04-01: 41; 2026-04-02: 41; 2026-04-03: 41; 2026-04-04: 41; 2026-04-05: 0; 2026-04-06: 34; 2026-04-07: 34; 2026-04-08: 34; 2026-04-09: 34; 2026-04-10: 32; 2026-04-11: 32; 2026-04-12: 0; 2026-04-13: 34; 2026-04-14: 34; 2026-04-15: 34; 2026-04-16: 34; 2026-04-17: 34; 2026-04-18: 34; 2026-04-19: 0; 2026-04-20: 34; 2026-04-21: 34; 2026-04-22: 34; 2026-04-23: 34; 2026-04-24: 34; 2026-04-25: 34; 2026-04-26: 0; 2026-04-27: 16; 2026-04-28: 16; 2026-04-29: 16; 2026-04-30: 16; 2026-05-01: 16; 2026-05-02: 16; 2026-05-03: 0; 2026-05-04: 14; 2026-05-05: 14; 2026-05-06: 14; 2026-05-07: 14; 2026-05-08: 14; 2026-05-09: 14; 2026-05-10: 0; 2026-05-11: 14; 2026-05-12: 14; 2026-05-13: 14; 2026-05-14: 14; 2026-05-15: 14; 2026-05-16: 14; 2026-05-17: 0; 2026-05-18: 12; 2026-05-19: 12; 2026-05-20: 12; 2026-05-21: 12; 2026-05-22: 12; 2026-05-23: 12; 2026-05-24: 0; 2026-05-25: 12; 2026-05-26: 12; 2026-05-27: 12; 2026-05-28: 12; 2026-05-29: 12; 2026-05-30: 12; 2026-05-31: 0
1 | 0 | 0 | 1.0.0 | E2 N | [8 empty] | 1610 |  |  |  |  | 2026-04-03 | 12.68% | 204.1889 | 2 |  | 48
1 | 1 | 0 | 1.1.0 | E2N Outside Windows | [8 empty] | 540 | [5 empty] | 2.374% | 12.8205 |  |  | 0
1 | 1 | 1 | 1.1.1 | Dismantling of Drywall + Al Sheet | 1 | MYA | A | 156 | 8 | 148 | 2 | 125 | 250 | 250 | 0 | 2025-12-08 | 40 | 2026-01-30 | 5.128% | 12.8205 | 0% | 40.8% | 102 |  | 2025-11-25: 2; 2025-12-08: 10; 2025-12-09: 10; 2025-12-10: 10; 2025-12-11: 10; 2025-12-12: 10; 2025-12-13: 10; 2025-12-15: 8; 2025-12-16: 8; 2025-12-17: 8; 2025-12-18: 8; 2025-12-19: 8; 2026-01-12: 10; 2026-01-13: 10; 2026-01-14: 10; 2026-01-15: 10; 2026-01-16: 10; 2026-01-17: 10; 2026-01-19: 8; 2026-01-20: 8; 2026-01-21: 8; 2026-01-22: 8; 2026-01-23: 8; 2026-01-24: 8; 2026-01-26: 8; 2026-01-27: 8; 2026-01-28: 6; 2026-01-29: 6; 2026-01-30: 6; 2026-01-31: 6
1 | 1 | 2 | 1.1.2 | Application of New Membrane | 1 | MYA | A | 156 | 0 | 156 | 2 | 80 | 160 | 164 | -4 | 2025-12-15 | 45 | 2026-02-13 | 0% | 0 | 0% | 7.5% | 12 |  | 2025-12-15: 2; 2025-12-16: 2; 2025-12-17: 2; 2025-12-18: 2; 2025-12-19: 4; 2026-01-12: 8; 2026-01-13: 8; 2026-01-14: 8; 2026-01-15: 8; 2026-01-16: 8; 2026-01-17: 8; 2026-01-19: 6; 2026-01-20: 6; 2026-01-21: 6; 2026-01-22: 6; 2026-01-23: 6; 2026-01-24: 6; 2026-01-26: 4; 2026-01-27: 4; 2026-01-28: 6; 2026-01-29: 6; 2026-01-30: 6; 2026-01-31: 6; 2026-02-02: 4; 2026-02-03: 4; 2026-02-04: 4; 2026-02-05: 4; 2026-02-06: 4; 2026-02-07: 4; 2026-02-09: 2; 2026-02-10: 2; 2026-02-11: 2; 2026-02-12: 2; 2026-02-13: 2; 2026-02-14: 2
1 | 1 | 3 | 1.1.3 | Installation of Al. Sheet | 1 | MYA | A | 156 | 0 | 156 | 2 | 65 | 130 | 132 | -2 | 2026-01-19 | 20 | 2026-02-13 | 0% | 0 | 0% | 0% | 0 |  | 2026-01-19: 4; 2026-01-20: 4; 2026-01-21: 4; 2026-01-22: 4; 2026-01-23: 4; 2026-01-24: 4; 2026-01-26: 4; 2026-01-27: 4; 2026-01-28: 4; 2026-01-29: 4; 2026-01-30: 4; 2026-01-31: 4; 2026-02-02: 6; 2026-02-03: 6; 2026-02-04: 6; 2026-02-05: 6; 2026-02-06: 6; 2026-02-07: 6; 2026-02-09: 8; 2026-02-10: 8; 2026-02-11: 8; 2026-02-12: 8; 2026-02-13: 8; 2026-02-14: 8
1 | 1 | 4 | 1.1.4 | Installation of New Drywall | 1 | XXX | A | 156 | 0 | 156 |  |  | 0 | 0 | 0 |  |  |  | 0% | 0 |  |  | 0
1 | 2 | 0 | 1.2.0 | E2N Courtyard Windows | [8 empty] | 160 | [5 empty] | 79.61% | 127.3684 |  |  | 0
1 | 2 | 1 | 1.2.1 | Dismantling of Drywall | 1 | MYA | A | 76 | 76 | 0 | 10 | 8 | 80 | 80 | 0 | 2025-11-24 | 20 | 2025-12-19 | 100% | 80 | 0% | 100% | 80 |  | 2025-11-24: 2; 2025-11-25: 3; 2025-11-26: 3; 2025-11-27: 2; 2025-11-28: 2; 2025-11-29: 2; 2025-12-01: 4; 2025-12-02: 4; 2025-12-03: 4; 2025-12-04: 4; 2025-12-05: 4; 2025-12-06: 4; 2025-12-08: 4; 2025-12-09: 4; 2025-12-10: 4; 2025-12-11: 4; 2025-12-12: 4; 2025-12-13: 4; 2025-12-15: 4; 2025-12-16: 4; 2025-12-17: 4; 2025-12-18: 4; 2025-12-19: 2
1 | 2 | 2 | 1.2.2 | Application of New Membrane | 1 | MYA | A | 76 | 45 | 31 | 10 | 8 | 80 | 44 | 36 | 2025-12-08 | 10 | 2025-12-19 | 59.21% | 47.3684 | 0% | 55% | 44 |  | 2025-12-08: 4; 2025-12-09: 4; 2025-12-10: 4; 2025-12-11: 4; 2025-12-12: 4; 2025-12-13: 4; 2025-12-15: 4; 2025-12-16: 4; 2025-12-17: 4; 2025-12-18: 4; 2025-12-19: 4
1 | 2 | 3 | 1.2.3 | Installation of New Drywall | 1 | XXX | A | 76 | 0 | 76 |  |  | 0 | 0 | 0 |  |  |  | 0% | 0 |  |  | 0
1 | 3 | 0 | 1.3.0 | Garage entrance aluminum cladding (north) |  | MYA | B | 1 | 1 | 0 | 4 | 6 | 24 |  |  | 2025-12-01 | 5 | 2025-12-05 | 100% | 24 | 0% | 100% | 24 |  | 2025-12-01: 4; 2025-12-02: 4; 2025-12-03: 4; 2025-12-04: 4; 2025-12-05: 4; 2025-12-06: 4
1 | 4 | 0 | 1.4.0 | Hörmann Door (West) | [8 empty] | 24 | [5 empty] | 66.67% | 16 | 0% | 0% | 0
1 | 4 | 1 | 1.4.1 | Steel structure | 2 | MYA | B | 1 | 1 | 0 | 4 | 4 | 16 | 0 | 16 |  |  |  | 100% | 16 | 0% | 0% | 0
1 | 4 | 2 | 1.4.2 | Door | 2 | MYA | B | 1 | 0 | 1 | 4 | 2 | 8 | 8 | 0 | 2025-12-11 | 2 | 2025-12-12 | 0% | 0 | 0% | 100% | 8 |  | 2025-12-11: 4; 2025-12-12: 4
1 | 5 | 0 | 1.5.0 | FT-07 Glass Rotation and Gasket replacement (East-West) | 2,3,4 | MYA | A | 7 | 0 | 7 | 3 | 6 | 18 | 18 | 0 | 2026-01-19 | 5 | 2026-01-23 | 0% | 0 | 0% | 0% | 0 |  | 2026-01-19: 3; 2026-01-20: 3; 2026-01-21: 3; 2026-01-22: 3; 2026-01-23: 3; 2026-01-24: 3
1 | 6 | 0 | 1.6.0 | Breuninger facade –Bottom Al. Finishing Reinforcement | 2 | MYA | A | 30 | 30 | 0 | 2 | 6 | 12 | 12 | 0 | 2025-12-01 | 5 | 2025-12-05 | 100% | 12 | 0% | 100% | 12 |  | 2025-12-01: 2; 2025-12-02: 2; 2025-12-03: 2; 2025-12-04: 2; 2025-12-05: 2; 2025-12-06: 2
1 | 7 | 0 | 1.7.0 | RT02 Additional Balustrade Module (NTA) | 2 | MYA | C | 2 | 0 | 2 | 4 | 3 | 12 | 12 | 0 | 2026-01-26 | 3 | 2026-01-28 | 0% | 0 | 0% | 0% | 0 |  | 2026-01-26: 4; 2026-01-27: 4; 2026-01-28: 4
1 | 8 | 0 | 1.8.0 | FT-13 Canopy – Anodized Al. Sheet Replacement + Cap Replacement | 2.3 | MYA | B | 60 | 0 | 60 | 4 | 6 | 24 | 0 | 24 |  |  |  | 0% | 0 | 0% | 0% | 0
1 | 9 | 0 | 1.9.0 | E2N - E3 Attika Connection Detail (East+North) | 2 | MYA | B | 2 | 0 | 2 | 2 | 4 | 8 | 12 | -4 | 2026-01-29 | 2 | 2026-01-30 | 0% | 0 | 0% | 0% | 0 |  | 2026-01-29: 4; 2026-01-30: 4; 2026-01-31: 4
1 | 10 | 0 | 1.10.0 | E2N East Stone FT15 Connection Detail | 2 | MYA | A | 1 | 1 | 0 | 2 | 6 | 12 | 12 | 0 | 2025-12-01 | 5 | 2025-12-05 | 100% | 12 | 0% | 100% | 12 |  | 2025-12-01: 2; 2025-12-02: 2; 2025-12-03: 2; 2025-12-04: 2; 2025-12-05: 2; 2025-12-06: 2
1 | 11 | 0 | 1.11.0 | General – Glass replacement | 2,3,4 | MYA | B | 9 | 0 | 9 | 4 | 5 | 20 | 0 | 20 |  |  |  | 0% | 0 | 0% | 0% | 0
1 | 12 | 0 | 1.12.0 | FT-18 | [8 empty] | 504 | [5 empty] | 0% | 0 | 0% | 0% | 0
1 | 12 | 1 | 1.12.1 | Paint repair and bolt replacement | 2.5 | MYA | A | 1 | 0 | 1 | 10 | 48 | 480 | 480 | 0 | 2026-02-02 | 40 | 2026-03-27 | 0% | 0 | 0% | 0% | 0 |  | 2026-02-02: 10; 2026-02-03: 10; 2026-02-04: 10; 2026-02-05: 10; 2026-02-06: 10; 2026-02-07: 10; 2026-02-09: 10; 2026-02-10: 10; 2026-02-11: 10; 2026-02-12: 10; 2026-02-13: 10; 2026-02-14: 10; 2026-02-16: 10; 2026-02-17: 10; 2026-02-18: 10; 2026-02-19: 10; 2026-02-20: 10; 2026-02-21: 10; 2026-02-23: 10; 2026-02-24: 10; 2026-02-25: 10; 2026-02-26: 10; 2026-02-27: 10; 2026-02-28: 10; 2026-03-02: 10; 2026-03-03: 10; 2026-03-04: 10; 2026-03-05: 10; 2026-03-06: 10; 2026-03-07: 10; 2026-03-09: 10; 2026-03-10: 10; 2026-03-11: 10; 2026-03-12: 10; 2026-03-13: 10; 2026-03-14: 10; 2026-03-16: 10; 2026-03-17: 10; 2026-03-18: 10; 2026-03-19: 10; 2026-03-20: 10; 2026-03-21: 10; 2026-03-23: 10; 2026-03-24: 10; 2026-03-25: 10; 2026-03-26: 10; 2026-03-27: 10; 2026-03-28: 10
1 | 12 | 2 | 1.12.2 | 1141 Parcel / Passage and parapet installation (NTA) | 2,3,4,5 | MYA | B | 1 | 0 | 1 | 4 | 6 | 24 | 24 | 0 | 2026-02-09 | 5 | 2026-02-13 | 0% | 0 | 0% | 0% | 0 |  | 2026-02-09: 4; 2026-02-10: 4; 2026-02-11: 4; 2026-02-12: 4; 2026-02-13: 4; 2026-02-14: 4
1 | 13 | 0 | 1.13.0 | Acoustic Roof FT-18 (NTA) | [8 empty] | 252 | [5 empty] | 0% | 0 | 0% | 0% | 0
1 | 13 | 1 | 1.13.1 | Installed Steel Drilling + Paint Touch up | 2,3,4,5 | MYA | C | 1 | 0 | 1 | 4 | 18 | 72 | 72 | 0 | 2026-02-23 | 15 | 2026-03-13 | 0% | 0 | 0% | 0% | 0 |  | 2026-02-23: 4; 2026-02-24: 4; 2026-02-25: 4; 2026-02-26: 4; 2026-02-27: 4; 2026-02-28: 4; 2026-03-02: 4; 2026-03-03: 4; 2026-03-04: 4; 2026-03-05: 4; 2026-03-06: 4; 2026-03-07: 4; 2026-03-09: 4; 2026-03-10: 4; 2026-03-11: 4; 2026-03-12: 4; 2026-03-13: 4; 2026-03-14: 4
1 | 13 | 2 | 1.13.2 | Acoustic Roof Secondary Steel Installation | 2,3,4,5 | MYA | C | 1 | 0 | 1 | 4 | 18 | 72 | 72 | 0 | 2026-03-09 | 15 | 2026-03-27 | 0% | 0 | 0% | 0% | 0 |  | 2026-03-09: 4; 2026-03-10: 4; 2026-03-11: 4; 2026-03-12: 4; 2026-03-13: 4; 2026-03-14: 4; 2026-03-16: 4; 2026-03-17: 4; 2026-03-18: 4; 2026-03-19: 4; 2026-03-20: 4; 2026-03-21: 4; 2026-03-23: 4; 2026-03-24: 4; 2026-03-25: 4; 2026-03-26: 4; 2026-03-27: 4; 2026-03-28: 4
1 | 13 | 3 | 1.13.3 | Modül installation | 2,3,4,5 | MYA | C | 1 | 0 | 1 | 6 | 18 | 108 | 108 | 0 | 2026-03-16 | 15 | 2026-04-03 | 0% | 0 | 0% | 0% | 0 |  | 2026-03-16: 6; 2026-03-17: 6; 2026-03-18: 6; 2026-03-19: 6; 2026-03-20: 6; 2026-03-21: 6; 2026-03-23: 6; 2026-03-24: 6; 2026-03-25: 6; 2026-03-26: 6; 2026-03-27: 6; 2026-03-28: 6; 2026-03-30: 6; 2026-03-31: 6; 2026-04-01: 6; 2026-04-02: 6; 2026-04-03: 6; 2026-04-04: 6
1 | 14 | 0 | 1.14.0 | Documentation + Testing | [15 empty] | 0 |  |  | 0
1 | 14 | 1 | 1.14.1 | WT01 |  | MYA |  |  |  |  | 0 | 0 | 0 | [6 empty] | 0 |  |  | 0
1 | 14 | 2 | 1.14.2 | FT08 |  | MYA |  |  |  |  | 0 | 0 | 0 | [6 empty] | 0 |  |  | 0
1 | 14 | 3 | 1.14.3 | FT07 |  | MYA |  |  |  |  | 0 | 0 | 0 | [6 empty] | 0 |  |  | 0
[20 empty] | 0 |  |  | 0
2 | 0 | 0 | 2.0.0 | E2S Exterior | [8 empty] | 1101 |  |  |  |  | 2026-03-27 | 14.23% | 156.7035 |  |  | 12
2 | 1 | 0 | 2.1.0 | FT-02 Zigzak | [8 empty] | 15 | [5 empty] | 97.64% | 14.6464 | 0% | 0% | 0
2 | 1 | 1 | 2.1.1 | Zigzak Mängel (West) | 2.3 | MYA | A | 120 | 120 | 0 | 3 | 1 | 3 | 3 | 0 |  |  |  | 100% | 3 | 0% | 100% | 3 |  | 2025-11-24: 3
2 | 1 | 2 | 2.1.2 | Zigzak Mängel (South) | 2.3 | MYA | A | 80 | 77 | 3 | 2 | 3 | 6 | 0 | 6 |  |  |  | 96.25% | 5.775 | 0% | 0% | 0
2 | 1 | 3 | 2.1.3 | Zigzak Mängel (East) | 2.3 | MYA | A | 140 | 137 | 3 | 2 | 3 | 6 | 0 | 6 |  |  |  | 97.86% | 5.8714 | 0% | 0% | 0
2 | 2 | 0 | 2.2.0 | WT-1.5 | [8 empty] | 0 | [5 empty] | 100% | 0
2 | 2 | 1 | 2.2.1 | Mängel (Galvanized sheet end Membran) (West) | 2.3 | MYA | A | 45 | 45 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 100% | 0 |  |  | 0
2 | 3 | 0 | 2.3.0 | FT-05 | [8 empty] | 102 | [5 empty] | 35.29% | 36 | 0% | 0% | 0
2 | 3 | 1 | 2.3.1 | Glass installation | 2,3,4 | MYA | B | 5 | 0 | 5 | 4 | 3 | 12 | 12 | 0 | 2026-02-02 | 3 | 2026-02-04 | 0% | 0 | 0% | 0% | 0 |  | 2026-02-02: 4; 2026-02-03: 4; 2026-02-04: 4
2 | 3 | 2 | 2.3.2 | Membrane control (Big) | 2.3 | MYA | A | 6 | 0 | 6 | 3 | 30 | 90 | 81 | 9 | 2026-01-12 | 15 | 2026-01-30 | 0% | 0 | 0% | 0% | 0 |  | 2026-01-12: 6; 2026-01-13: 6; 2026-01-14: 6; 2026-01-15: 6; 2026-01-16: 6; 2026-01-17: 6; 2026-01-19: 3; 2026-01-20: 3; 2026-01-21: 3; 2026-01-22: 3; 2026-01-23: 3; 2026-01-24: 3; 2026-01-26: 3; 2026-01-27: 3; 2026-01-28: 3; 2026-01-29: 6; 2026-01-30: 6; 2026-01-31: 6
2 | 3 | 3 | 2.3.3 | Membrane control (Small) | 2.3 | MYA | A | 6 | 4 | 2 | 3 | 18 | 54 | 54 | 0 | 2025-11-24 | 48 | 2026-01-28 | 66.67% | 36 | 0% | 50% | 27 |  | 2025-11-24: 5; 2025-11-25: 5; 2025-11-26: 5; 2025-11-27: 4; 2025-11-28: 4; 2025-11-29: 4; 2026-01-19: 3; 2026-01-20: 3; 2026-01-21: 3; 2026-01-22: 3; 2026-01-23: 3; 2026-01-24: 3; 2026-01-26: 3; 2026-01-27: 3; 2026-01-28: 3
2 | 4 | 0 | 2.4.0 | Attika | [8 empty] | 102 | [5 empty] | 76.77% | 78.3037 | 0% | 0% | 0
2 | 4 | 1 | 2.4.1 | 7.OG | 2 | MYA | B | 200 | 191 | 9 | 5 | 3 | 15 | 15 | 0 | 2025-12-01 | 3 | 2025-12-03 | 95.5% | 14.325 | 0% | 100% | 15 |  | 2025-12-01: 5; 2025-12-02: 5; 2025-12-03: 5
2 | 4 | 2 | 2.4.2 | 5.OG | 2 | MYA | B | 24 | 23 | 1 | 5 | 3 | 15 | 15 | 0 | 2025-12-04 | 2 | 2025-12-05 | 95.83% | 14.375 | 0% | 100% | 15 |  | 2025-12-04: 5; 2025-12-05: 5; 2025-12-06: 5
2 | 4 | 3 | 2.4.3 | 3.OG | [8 empty] | 72 | 69 | 3 |  |  |  | 68.89% | 49.6037 | 0% | 0% | 0
2 | 4 | 4 | 2.4.3.1 | New Design - Coordination with Roofing (NTA) |  | MYA | [7 empty] | 0 | 0 |  |  |  |  | 0 |  |  | 0
2 | 4 | 5 | 2.4.3.2 | 3.OG Attika (West) | 2.3 | MYA | C | 28 | 16 | 12 | 3 | 12 | 36 | 33 | 3 | 2025-12-08 | 10 | 2025-12-19 | 57.14% | 20.5714 | 0% | 91.67% | 33 |  | 2025-12-08: 3; 2025-12-09: 3; 2025-12-10: 3; 2025-12-11: 3; 2025-12-12: 3; 2025-12-13: 3; 2025-12-15: 3; 2025-12-16: 3; 2025-12-17: 3; 2025-12-18: 3; 2025-12-19: 3; 2025-12-20: 0
2 | 4 | 6 | 2.4.3.3 | 3.OG Attika (East) | 2.3 | MYA | C | 31 | 25 | 6 | 3 | 12 | 36 | 36 | 0 | 2026-01-12 | 10 | 2026-01-23 | 80.65% | 29.0323 | 0% | 0% | 0 |  | 2026-01-12: 3; 2026-01-13: 3; 2026-01-14: 3; 2026-01-15: 3; 2026-01-16: 3; 2026-01-17: 3; 2026-01-19: 3; 2026-01-20: 3; 2026-01-21: 3; 2026-01-22: 3; 2026-01-23: 3; 2026-01-24: 3
2 | 5 | 0 | 2.5.0 | Steel substructure for ceramic tile installation (NTA) |  | MYA | C | 2 | 2 | 0 | 4 | 4 | 16 |  |  | 2025-11-27 | 2 | 2025-11-28 | 100% | 16 | 0% | 75% | 12 |  | 2025-11-27: 4; 2025-11-28: 4; 2025-11-29: 4
2 | 6 | 0 | 2.6.0 | FT-12 - Canopy (Pullman) | [8 empty] | 132 | [5 empty] | 0% | 0 | 0% | 0% | 0
2 | 6 | 1 | 2.6.1 | Steel installation | 2,3,4 | MYA | B | 40 | 0 | 40 | 5 | 12 | 60 | 60 | 0 | 2026-02-16 | 10 | 2026-02-27 | 0% | 0 | 0% | 0% | 0 |  | 2026-02-16: 5; 2026-02-17: 5; 2026-02-18: 5; 2026-02-19: 5; 2026-02-20: 5; 2026-02-21: 5; 2026-02-23: 5; 2026-02-24: 5; 2026-02-25: 5; 2026-02-26: 5; 2026-02-27: 5; 2026-02-28: 5
2 | 6 | 2 | 2.6.2 | Aluminium Substructure | 2,3,4 | MYA | B | 105 | 0 | 105 | 4 | 12 | 48 | 48 | 0 | 2026-03-02 | 10 | 2026-03-13 | 0% | 0 | 0% | 0% | 0 |  | 2026-03-02: 4; 2026-03-03: 4; 2026-03-04: 4; 2026-03-05: 4; 2026-03-06: 4; 2026-03-07: 4; 2026-03-09: 4; 2026-03-10: 4; 2026-03-11: 4; 2026-03-12: 4; 2026-03-13: 4; 2026-03-14: 4
2 | 6 | 3 | 2.6.3 | Aluminium Cladding | 2,3,4 | MYA | B | 143 | 0 | 143 | 4 | 6 | 24 | 24 | 0 | 2026-03-09 | 5 | 2026-03-13 | 0% | 0 | 0% | 0% | 0 |  | 2026-03-09: 4; 2026-03-10: 4; 2026-03-11: 4; 2026-03-12: 4; 2026-03-13: 4; 2026-03-14: 4
2 | 7 | 0 | 2.7.0 | Dorma - Sliding door track installation (East) |  | MYA | B | 1 | 0 | 1 | 2 | 3 | 6 | [5 empty] | 0% | 0 | 0% | 0% | 0
2 | 8 | 0 | 2.8.0 | FT14 Additional Spandrel Panel (NTA) | [8 empty] | 10 | [5 empty] | 0% | 0 | 0% | 0% | 0
2 | 8 | 1 | 2.8.1 | New Design |  | MYA | [13 empty] | 0
2 | 8 | 2 | 2.8.2 | Approval by SOB / NTA Approval by URW |  | SOB | [13 empty] | 0
2 | 8 | 3 | 2.8.3 | Procurement + Manufacturing |  | MYA |  | 2 | 0 | 2 |  |  | 0 | [5 empty] | 0% | 0
2 | 8 | 4 | 2.8.4 | Installation | 1 | MYA | C | 2 | 0 | 2 | 2 | 5 | 10 | 12 | -2 | 2026-02-16 | 5 | 2026-02-20 | 0% | 0 | 0% | 0% | 0 |  | 2026-02-16: 2; 2026-02-17: 2; 2026-02-18: 2; 2026-02-19: 2; 2026-02-20: 2; 2026-02-21: 2
2 | 9 | 0 | 2.9.0 | Additional Vent backside of Louver E2S West (NTA) | [8 empty] | 10 | [5 empty] | 0% | 0 | 0% | 0% | 0
2 | 9 | 1 | 2.9.1 | New Design |  | MYA | [13 empty] | 0 |  |  | 0
2 | 9 | 2 | 2.9.2 | Approval by SOB / NTA Approval by URW |  | SOB | [13 empty] | 0 |  |  | 0
2 | 9 | 3 | 2.9.3 | Procurement + Manufacturing |  | MYA |  | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  |  | 0% | 0 |  |  | 0
2 | 9 | 4 | 2.9.4 | Installation | 1.6 | MYA | C | 2 | 0 | 2 | 2 | 5 | 10 | 12 | -2 | 2026-02-16 | 5 | 2026-02-20 | 0% | 0 | 0% | 0% | 0 |  | 2026-02-16: 2; 2026-02-17: 2; 2026-02-18: 2; 2026-02-19: 2; 2026-02-20: 2; 2026-02-21: 2
2 | 10 | 0 | 2.10.0 | General – Glass replacement |  | MYA | B | 36 | 0 | 36 | 4 | 12 | 48 | [5 empty] | 0% | 0 | 0% | 0% | 0
2 | 11 | 0 | 2.11.0 | Interkom Glasses (NTA) |  | MYA | C | 6 | 0 | 6 | 4 | 6 | 24 | [5 empty] | 0% | 0 | 0% | 0% | 0
2 | 12 | 0 | 2.12.0 | FT-18 | [8 empty] | 588 | [5 empty] | 1.999% | 11.7534 | 0% | 0% | 0
2 | 12 | 1 | 2.12.1 | Module Installation | 2.6 | MYA | B | 146 | 143 | 3 | 4 | 3 | 12 | 12 | 0 | 2026-03-26 | 2 | 2026-03-27 | 97.95% | 11.7534 | 0% | 0% | 0 |  | 2026-03-26: 4; 2026-03-27: 4; 2026-03-28: 4
2 | 12 | 2 | 2.12.2 | Paint repair and bolt replacement | 2.5 | MYA | A | 1 | 0 | 1 | 10 | 48 | 480 | 480 | 0 | 2026-02-02 | 40 | 2026-03-27 | 0% | 0 | 0% | 0% | 0 |  | 2026-02-02: 10; 2026-02-03: 10; 2026-02-04: 10; 2026-02-05: 10; 2026-02-06: 10; 2026-02-07: 10; 2026-02-09: 10; 2026-02-10: 10; 2026-02-11: 10; 2026-02-12: 10; 2026-02-13: 10; 2026-02-14: 10; 2026-02-16: 10; 2026-02-17: 10; 2026-02-18: 10; 2026-02-19: 10; 2026-02-20: 10; 2026-02-21: 10; 2026-02-23: 10; 2026-02-24: 10; 2026-02-25: 10; 2026-02-26: 10; 2026-02-27: 10; 2026-02-28: 10; 2026-03-02: 10; 2026-03-03: 10; 2026-03-04: 10; 2026-03-05: 10; 2026-03-06: 10; 2026-03-07: 10; 2026-03-09: 10; 2026-03-10: 10; 2026-03-11: 10; 2026-03-12: 10; 2026-03-13: 10; 2026-03-14: 10; 2026-03-16: 10; 2026-03-17: 10; 2026-03-18: 10; 2026-03-19: 10; 2026-03-20: 10; 2026-03-21: 10; 2026-03-23: 10; 2026-03-24: 10; 2026-03-25: 10; 2026-03-26: 10; 2026-03-27: 10; 2026-03-28: 10
2 | 12 | 3 | 2.12.3 | Trapezoidal sheet installation | 2.5 | MYA | B | 265 | 0 | 265 | 4 | 24 | 96 | 96 | 0 | 2026-03-16 | 10 | 2026-03-27 | 0% | 0 | 0% | 0% | 0 |  | 2026-03-16: 8; 2026-03-17: 8; 2026-03-18: 8; 2026-03-19: 8; 2026-03-20: 8; 2026-03-21: 8; 2026-03-23: 8; 2026-03-24: 8; 2026-03-25: 8; 2026-03-26: 8; 2026-03-27: 8; 2026-03-28: 8
2 | 13 | 0 | 2.13.0 | Doors | [8 empty] | 48 | [5 empty] | 0% | 0 | 0% | 0% | 0
2 | 13 | 1 | 2.13.1 | Terminal Doors | 2 | MYA | A | 12 | 0 | 12 | 4 | 12 | 48 | 0 | 48 |  |  |  | 0% | 0 | 0% | 0% | 0
2 | 13 | 2 | 2.13.2 | Hotel Doors | 2 | MYA | A | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  |  | 0% | 0 |  |  | 0
[20 empty] | 0 |  |  | 0
3 | 0 | 0 | 3.0.0 | E2S Inenhof | [8 empty] | 936 |  |  |  |  | 2026-05-29 | 0% | 0 |  |  | 0
3 | 1 | 0 | 3.1.0 | WT-04 | [8 empty] | 108 | [5 empty] | 0% | 0 | 0% | 0% | 0
3 | 1 | 1 | 3.1.1 | Schüco adaptör profile | 2.6 | MYA | A | 62 | 0 | 62 | 2 | 18 | 36 | 36 | 0 | 2026-02-16 | 15 | 2026-03-06 | 0% | 0 | 0% | 0% | 0 |  | 2026-02-16: 2; 2026-02-17: 2; 2026-02-18: 2; 2026-02-19: 2; 2026-02-20: 2; 2026-02-21: 2; 2026-02-23: 2; 2026-02-24: 2; 2026-02-25: 2; 2026-02-26: 2; 2026-02-27: 2; 2026-02-28: 2; 2026-03-02: 2; 2026-03-03: 2; 2026-03-04: 2; 2026-03-05: 2; 2026-03-06: 2; 2026-03-07: 2
3 | 1 | 2 | 3.1.2 | Stone Installation | 2.6 | MYA | A | 53 | 0 | 53 | 4 | 6 | 24 | 24 | 0 | 2026-02-16 | 5 | 2026-02-20 | 0% | 0 | 0% | 0% | 0 |  | 2026-02-16: 4; 2026-02-17: 4; 2026-02-18: 4; 2026-02-19: 4; 2026-02-20: 4; 2026-02-21: 4
3 | 1 | 3 | 3.1.3 | Glass installation | 2.6 | MYA | A | 5 | 0 | 5 | 4 | 6 | 24 | 24 | 0 | 2026-02-23 | 5 | 2026-02-27 | 0% | 0 | 0% | 0% | 0 |  | 2026-02-23: 4; 2026-02-24: 4; 2026-02-25: 4; 2026-02-26: 4; 2026-02-27: 4; 2026-02-28: 4
3 | 1 | 4 | 3.1.4 | Cocoon-Coordination* Depending on them | 2.6 | MYA | A | 1 | 0 | 1 | 2 | 12 | 24 | 6 | 18 |  |  |  | 0% | 0 | 0% | 25% | 6 |  | 2025-11-24: 2; 2025-11-25: 2; 2025-11-26: 2
3 | 2 | 0 | 3.2.0 | WT-1.5 | [8 empty] | 12 | [5 empty] | 0% | 0 | 0% | 0% | 0
3 | 2 | 1 | 3.2.1 | Mängel (Galvanized sheet end Membran) (West) | 2.6 | MYA | A | 33 | 33 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 100% | 0 |  |  | 0
3 | 2 | 2 | 3.2.2 | Schüco adaptör profile | 2.6 | MYA | A | 18 | 0 | 18 | 2 | 6 | 12 | 12 | 0 | 2026-03-16 | 5 | 2026-03-20 | 0% | 0 | 0% | 0% | 0 |  | 2026-03-16: 2; 2026-03-17: 2; 2026-03-18: 2; 2026-03-19: 2; 2026-03-20: 2; 2026-03-21: 2
3 | 3 | 0 | 3.3.0 | FT-03 | [8 empty] | 186 | [5 empty] | 0% | 0 | 0% | 0% | 0
3 | 3 | 1 | 3.3.1 | Phonotherm structural board + Flashing Installation. | 2 | MYA | B | 107 | 0 | 107 | 2 | 18 | 36 | 36 | 0 | 2026-03-16 | 15 | 2026-04-03 | 0% | 0 | 0% | 0% | 0 |  | 2026-03-16: 2; 2026-03-17: 2; 2026-03-18: 2; 2026-03-19: 2; 2026-03-20: 2; 2026-03-21: 2; 2026-03-23: 2; 2026-03-24: 2; 2026-03-25: 2; 2026-03-26: 2; 2026-03-27: 2; 2026-03-28: 2; 2026-03-30: 2; 2026-03-31: 2; 2026-04-01: 2; 2026-04-02: 2; 2026-04-03: 2; 2026-04-04: 2
3 | 3 | 2 | 3.3.2 | Glass Installation - Pressure + Cover | 1,2,7,8 | MYA | B | 27 | 0 | 27 | 5 | 6 | 30 | 30 | 0 | 2026-03-30 | 5 | 2026-04-03 | 0% | 0 | 0% | 0% | 0 |  | 2026-03-30: 5; 2026-03-31: 5; 2026-04-01: 5; 2026-04-02: 5; 2026-04-03: 5; 2026-04-04: 5
3 | 3 | 3 | 3.3.3 | Aluminum sheet under the console end ceramic back, steel construction (East-West) | 2,6,7,8 | MYA | B | 38 | 0 | 38 | 4 | 24 | 96 | 96 | 0 | 2026-03-02 | 10 | 2026-03-13 | 0% | 0 | 0% | 0% | 0 |  | 2026-03-02: 8; 2026-03-03: 8; 2026-03-04: 8; 2026-03-05: 8; 2026-03-06: 8; 2026-03-07: 8; 2026-03-09: 8; 2026-03-10: 8; 2026-03-11: 8; 2026-03-12: 8; 2026-03-13: 8; 2026-03-14: 8
3 | 3 | 4 | 3.3.4 | Top Finish Attika (Anc+Const.+Membr+Sheet) (North) | 2 | MYA | B | 39 | 0 | 39 | 2 | 6 | 12 | 12 | 0 | 2026-03-23 | 8 | 2026-04-01 | 0% | 0 | 0% | 0% | 0 |  | 2026-03-23: 2; 2026-03-24: 2; 2026-03-25: 2; 2026-03-30: 2; 2026-03-31: 2; 2026-04-01: 2
3 | 3 | 5 | 3.3.5 | Installation of steel construction behind stone cladding (South) | 2.6 | MYA | B | 30 | 0 | 30 | 2 | 6 | 12 | 12 | 0 | 2026-03-23 | 8 | 2026-04-01 | 0% | 0 | 0% | 0% | 0 |  | 2026-03-23: 2; 2026-03-24: 2; 2026-03-25: 2; 2026-03-30: 2; 2026-03-31: 2; 2026-04-01: 2
3 | 4 | 0 | 3.4.0 | RT-01 Glass Balustrade | [8 empty] | 150 | [5 empty] | 0% | 0 | 0% | 0% | 0
3 | 4 | 1 | 3.4.1 | Brackets (NTA) | 2 | MYA | C | 173 | 0 | 173 | 3 | 18 | 54 | 54 | 0 | 2026-01-26 | 10 | 2026-02-06 | 0% | 0 | 0% | 0% | 0 |  | 2026-01-26: 6; 2026-01-27: 6; 2026-01-28: 6; 2026-01-29: 6; 2026-01-30: 6; 2026-01-31: 6; 2026-02-02: 3; 2026-02-03: 3; 2026-02-04: 3; 2026-02-05: 3; 2026-02-06: 3; 2026-02-07: 3
3 | 4 | 2 | 3.4.2 | Roofing Works |  | HOE | [7 empty] | 0 | 0 |  |  |  |  | 0 |  |  | 0
3 | 4 | 3 | 3.4.3 | Steel Construction | 2 | MYA | B | 173 | 0 | 173 | 2 | 6 | 12 | 12 | 0 | 2026-03-30 | 5 | 2026-04-03 | 0% | 0 | 0% | 0% | 0 |  | 2026-03-30: 2; 2026-03-31: 2; 2026-04-01: 2; 2026-04-02: 2; 2026-04-03: 2; 2026-04-04: 2
3 | 4 | 4 | 3.4.4 | Aluminum Module | 2 | MYA | B | 62 | 0 | 62 | 2 | 6 | 12 | 12 | 0 | 2026-03-30 | 5 | 2026-04-03 | 0% | 0 | 0% | 0% | 0 |  | 2026-03-30: 2; 2026-03-31: 2; 2026-04-01: 2; 2026-04-02: 2; 2026-04-03: 2; 2026-04-04: 2
3 | 4 | 5 | 3.4.5 | Attika Installation | 2 | MYA | B | 62 | 0 | 62 | 2 | 12 | 24 | 24 | 0 | 2026-04-02 | 5 | 2026-04-08 | 0% | 0 | 0% | 0% | 0 |  | 2026-04-02: 4; 2026-04-03: 4; 2026-04-04: 4; 2026-04-06: 4; 2026-04-07: 4; 2026-04-08: 4
3 | 4 | 6 | 3.4.6 | Glass installation | 2.8 | MYA | B | 103 | 0 | 103 | 4 | 12 | 48 | 48 | 0 | 2026-04-06 | 10 | 2026-04-17 | 0% | 0 | 0% | 0% | 0 |  | 2026-04-06: 4; 2026-04-07: 4; 2026-04-08: 4; 2026-04-09: 4; 2026-04-10: 4; 2026-04-11: 4; 2026-04-13: 4; 2026-04-14: 4; 2026-04-15: 4; 2026-04-16: 4; 2026-04-17: 4; 2026-04-18: 4
3 | 5 | 0 | 3.5.0 | FT16 A + B | [8 empty] | 168 | [5 empty] | 0% | 0 | 0% | 0% | 0
3 | 5 | 1 | 3.5.1 | Secondary Steel Construction (NTA) |  | MYA |  | 1 | 0 | 1 | [8 empty] | 0% | 0 |  |  | 0
3 | 5 | 2 | 3.5.2 | Design + Static Calculation |  | MYA |  | 1 | 0 | 1 | [8 empty] | 0% | 0 |  |  | 0
3 | 5 | 3 | 3.5.3 | Procurement + Manufacturing |  | MYA |  | 1 | 0 | 1 | [8 empty] | 0% | 0 |  |  | 0
3 | 5 | 4 | 3.5.4 | Installation | 2,6,8 | MYA | C | 1 | 0 | 1 | 4 | 12 | 48 | 48 | 0 | 2026-03-30 | 10 | 2026-04-10 | 0% | 0 | 0% | 0% | 0 |  | 2026-03-30: 4; 2026-03-31: 4; 2026-04-01: 4; 2026-04-02: 4; 2026-04-03: 4; 2026-04-04: 4; 2026-04-06: 4; 2026-04-07: 4; 2026-04-08: 4; 2026-04-09: 4; 2026-04-10: 4; 2026-04-11: 4
3 | 5 | 5 | 3.5.5 | Brackets | 2,6,8 | MYA | B | 162 | 0 | 162 | 4 | 12 | 48 | 48 | 0 | 2026-03-30 | 10 | 2026-04-10 | 0% | 0 | 0% | 0% | 0 |  | 2026-03-30: 4; 2026-03-31: 4; 2026-04-01: 4; 2026-04-02: 4; 2026-04-03: 4; 2026-04-04: 4; 2026-04-06: 4; 2026-04-07: 4; 2026-04-08: 4; 2026-04-09: 4; 2026-04-10: 4; 2026-04-11: 4
3 | 5 | 6 | 3.5.6 | Aluminium Profiles | 2,6,8 | MYA | B | 95 | 0 | 95 | 4 | 6 | 24 | 24 | 0 | 2026-04-06 | 5 | 2026-04-10 | 0% | 0 | 0% | 0% | 0 |  | 2026-04-06: 4; 2026-04-07: 4; 2026-04-08: 4; 2026-04-09: 4; 2026-04-10: 4; 2026-04-11: 4
3 | 5 | 7 | 3.5.7 | Aluminium Cladding | 2,6,8 | MYA | B | 121 | 0 | 121 | 4 | 12 | 48 | 48 | 0 | 2026-04-13 | 10 | 2026-04-24 | 0% | 0 | 0% | 0% | 0 |  | 2026-04-13: 4; 2026-04-14: 4; 2026-04-15: 4; 2026-04-16: 4; 2026-04-17: 4; 2026-04-18: 4; 2026-04-20: 4; 2026-04-21: 4; 2026-04-22: 4; 2026-04-23: 4; 2026-04-24: 4; 2026-04-25: 4
3 | 6 | 0 | 3.6.0 | FT17 | [8 empty] | 312 | [5 empty] | 0% | 0 | 0% | 0% | 0
3 | 6 | 1 | 3.6.1 | MEP + Other Works Completion |  | URW | [13 empty] | 0 |  |  | 0
3 | 6 | 2 | 3.6.2 | Brackets | 2,6,8 | MYA | B | 1673 | 0 | 1673 | 4 | 30 | 120 | 120 | 0 | 2026-04-27 | 15 | 2026-05-15 | 0% | 0 | 0% | 0% | 0 |  | 2026-04-27: 8; 2026-04-28: 8; 2026-04-29: 8; 2026-04-30: 8; 2026-05-01: 8; 2026-05-02: 8; 2026-05-04: 8; 2026-05-05: 8; 2026-05-06: 8; 2026-05-07: 8; 2026-05-08: 8; 2026-05-09: 8; 2026-05-11: 4; 2026-05-12: 4; 2026-05-13: 4; 2026-05-14: 4; 2026-05-15: 4; 2026-05-16: 4
3 | 6 | 3 | 3.6.3 | Aluminium Profiles | 2,6,8 | MYA | B | 1245 | 0 | 1245 | 4 | 12 | 48 | 48 | 0 | 2026-05-04 | 10 | 2026-05-15 | 0% | 0 | 0% | 0% | 0 |  | 2026-05-04: 4; 2026-05-05: 4; 2026-05-06: 4; 2026-05-07: 4; 2026-05-08: 4; 2026-05-09: 4; 2026-05-11: 4; 2026-05-12: 4; 2026-05-13: 4; 2026-05-14: 4; 2026-05-15: 4; 2026-05-16: 4
3 | 6 | 4 | 3.6.4 | Aluminium Cladding | 2,6,8 | MYA | B | 493 | 0 | 493 | 4 | 36 | 144 | 144 | 0 | 2026-05-11 | 15 | 2026-05-29 | 0% | 0 | 0% | 0% | 0 |  | 2026-05-11: 4; 2026-05-12: 4; 2026-05-13: 4; 2026-05-14: 4; 2026-05-15: 4; 2026-05-16: 4; 2026-05-18: 10; 2026-05-19: 10; 2026-05-20: 10; 2026-05-21: 10; 2026-05-22: 10; 2026-05-23: 10; 2026-05-25: 10; 2026-05-26: 10; 2026-05-27: 10; 2026-05-28: 10; 2026-05-29: 10; 2026-05-30: 10
[20 empty] | 0 |  |  | 0
4 | 0 | 0 | 4.0.0 | E2S Interior | [8 empty] | 522 |  |  |  |  | 2026-04-24 | 1.533% | 8 |  |  | 0
4 | 1 | 0 | 4.1.0 | FT15 Terminal Cable Canals (NTA) | [8 empty] | 24 | [5 empty] | 0% | 0 | 0% | 0% | 0
4 | 1 | 1 | 4.1.1 | New Design |  | MYA | [13 empty] | 0 |  |  | 0
4 | 1 | 2 | 4.1.2 | Approval by SOB / NTA Approval by URW |  | URW | [13 empty] | 0 |  |  | 0
4 | 1 | 3 | 4.1.3 | Procurement + Manufacturing |  | MYA |  | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  |  | 0% | 0 |  |  | 0
4 | 1 | 4 | 4.1.4 | Installation | 1.5 | MYA | C | 10 | 0 | 10 | 2 | 12 | 24 | 0 | 24 |  |  |  | 0% | 0 | 0% | 0% | 0
4 | 2 | 0 | 4.2.0 | WT-04 | [8 empty] | 96 | [5 empty] | 0% | 0 | 0% | 0% | 0
4 | 2 | 1 | 4.2.1 | Window Handle Installation + Adjustment | 1 | MYA | B | 214 | 0 | 214 | 2 | 24 | 48 | 48 | 0 | 2026-03-30 | 10 | 2026-04-10 | 0% | 0 | 0% | 0% | 0 |  | 2026-03-30: 4; 2026-03-31: 4; 2026-04-01: 4; 2026-04-02: 4; 2026-04-03: 4; 2026-04-04: 4; 2026-04-06: 4; 2026-04-07: 4; 2026-04-08: 4; 2026-04-09: 4; 2026-04-10: 4; 2026-04-11: 4
4 | 2 | 2 | 4.2.2 | Silicone/Gasket Control + Rectafication | 1 | MYA | A | 90 | 0 | 90 | 2 | 12 | 24 | 24 | 0 | 2026-04-09 | 5 | 2026-04-15 | 0% | 0 | 0% | 0% | 0 |  | 2026-04-09: 4; 2026-04-10: 4; 2026-04-11: 4; 2026-04-13: 4; 2026-04-14: 4; 2026-04-15: 4
4 | 2 | 3 | 4.2.3 | Interior Membrane Check + Touchup | 1 | MYA | A | 90 | 0 | 90 | 2 | 12 | 24 | 24 | 0 | 2026-04-16 | 5 | 2026-04-22 | 0% | 0 | 0% | 0% | 0 |  | 2026-04-16: 4; 2026-04-17: 4; 2026-04-18: 4; 2026-04-20: 4; 2026-04-21: 4; 2026-04-22: 4
4 | 3 | 0 | 4.3.0 | WT-1.5 | [8 empty] | 72 | [5 empty] | 0% | 0 | 0% | 0% | 0
4 | 3 | 1 | 4.3.1 | Window Handle Installation + Adjustment | 1 | MYA | B | 96 | 0 | 96 | 2 | 12 | 24 | 24 | 0 | 2026-04-13 | 10 | 2026-04-24 | 0% | 0 | 0% | 0% | 0 |  | 2026-04-13: 2; 2026-04-14: 2; 2026-04-15: 2; 2026-04-16: 2; 2026-04-17: 2; 2026-04-18: 2; 2026-04-20: 2; 2026-04-21: 2; 2026-04-22: 2; 2026-04-23: 2; 2026-04-24: 2; 2026-04-25: 2
4 | 3 | 2 | 4.3.2 | Silicone/Gasket Control + Rectafication | 1 | MYA | A | 78 | 0 | 78 | 2 | 12 | 24 | 24 | 0 | 2026-04-13 | 10 | 2026-04-24 | 0% | 0 | 0% | 0% | 0 |  | 2026-04-13: 2; 2026-04-14: 2; 2026-04-15: 2; 2026-04-16: 2; 2026-04-17: 2; 2026-04-18: 2; 2026-04-20: 2; 2026-04-21: 2; 2026-04-22: 2; 2026-04-23: 2; 2026-04-24: 2; 2026-04-25: 2
4 | 3 | 3 | 4.3.3 | Interior Membrane Check + Touchup | 1 | MYA | A | 78 | 0 | 78 | 2 | 12 | 24 | 24 | 0 | 2026-04-13 | 10 | 2026-04-24 | 0% | 0 | 0% | 0% | 0 |  | 2026-04-13: 2; 2026-04-14: 2; 2026-04-15: 2; 2026-04-16: 2; 2026-04-17: 2; 2026-04-18: 2; 2026-04-20: 2; 2026-04-21: 2; 2026-04-22: 2; 2026-04-23: 2; 2026-04-24: 2; 2026-04-25: 2
4 | 4 | 0 | 4.4.0 | FT-02 Zigzak | [8 empty] | 72 | [5 empty] | 0% | 0 | 0% | 0% | 0
4 | 4 | 1 | 4.4.1 | Window Handle Installation + Adjustment | 1 | MYA | B | 33 | 0 | 33 | 3 | 12 | 36 | 36 | 0 | 2026-04-13 | 5 | 2026-04-17 | 0% | 0 | 0% | 0% | 0 |  | 2026-04-13: 6; 2026-04-14: 6; 2026-04-15: 6; 2026-04-16: 6; 2026-04-17: 6; 2026-04-18: 6
4 | 4 | 2 | 4.4.2 | Silicone/Gasket Control + Rectafication | 1 | MYA | A | 255 | 0 | 255 | 2 | 6 | 12 | 12 | 0 | 2026-03-30 | 5 | 2026-04-03 | 0% | 0 | 0% | 0% | 0 |  | 2026-03-30: 2; 2026-03-31: 2; 2026-04-01: 2; 2026-04-02: 2; 2026-04-03: 2; 2026-04-04: 2
4 | 4 | 3 | 4.4.3 | Interior Membrane Check + Touchup | 1 | MYA | A | 79 | 0 | 79 | 2 | 12 | 24 | 24 | 0 | 2026-03-30 | 10 | 2026-04-10 | 0% | 0 | 0% | 0% | 0 |  | 2026-03-30: 2; 2026-03-31: 2; 2026-04-01: 2; 2026-04-02: 2; 2026-04-03: 2; 2026-04-04: 2; 2026-04-06: 2; 2026-04-07: 2; 2026-04-08: 2; 2026-04-09: 2; 2026-04-10: 2; 2026-04-11: 2
4 | 5 | 0 | 4.5.0 | FT-14 | [8 empty] | 24 | [5 empty] | 0% | 0 | 0% | 0% | 0
4 | 5 | 1 | 4.5.1 | Aluminum sheet installation | 1 | MYA | B | 43 | 0 | 43 | 2 | 6 | 12 | 12 | 0 | 2026-04-20 | 5 | 2026-04-24 | 0% | 0 | 0% | 0% | 0 |  | 2026-04-20: 2; 2026-04-21: 2; 2026-04-22: 2; 2026-04-23: 2; 2026-04-24: 2; 2026-04-25: 2
4 | 5 | 2 | 4.5.2 | Window Handle Installation + Adjustment | 1 | MYA | B | 43 | 0 | 43 | 2 | 6 | 12 | 12 | 0 | 2026-04-20 | 5 | 2026-04-24 | 0% | 0 | 0% | 0% | 0 |  | 2026-04-20: 2; 2026-04-21: 2; 2026-04-22: 2; 2026-04-23: 2; 2026-04-24: 2; 2026-04-25: 2
4 | 6 | 0 | 4.6.0 | FT-05 | [8 empty] | 24 | [5 empty] | 0% | 0 | 0% | 0% | 0
4 | 6 | 1 | 4.6.1 | Membrane Control + Rectafication | 1 | MYA | A | 18 | 0 | 18 | 2 | 12 | 24 | 24 | 0 | 2026-04-13 | 10 | 2026-04-24 | 0% | 0 | 0% | 0% | 0 |  | 2026-04-13: 2; 2026-04-14: 2; 2026-04-15: 2; 2026-04-16: 2; 2026-04-17: 2; 2026-04-18: 2; 2026-04-20: 2; 2026-04-21: 2; 2026-04-22: 2; 2026-04-23: 2; 2026-04-24: 2; 2026-04-25: 2
4 | 7 | 0 | 4.7.0 | FT-03 | [8 empty] | 84 | [5 empty] | 0% | 0 | 0% | 0% | 0
4 | 7 | 1 | 4.7.1 | Aluminum sheet installation | 1 | MYA | B | 107 | 0 | 107 | 2 | 12 | 24 | 24 | 0 | 2026-04-13 | 10 | 2026-04-24 | 0% | 0 | 0% | 0% | 0 |  | 2026-04-13: 2; 2026-04-14: 2; 2026-04-15: 2; 2026-04-16: 2; 2026-04-17: 2; 2026-04-18: 2; 2026-04-20: 2; 2026-04-21: 2; 2026-04-22: 2; 2026-04-23: 2; 2026-04-24: 2; 2026-04-25: 2
4 | 7 | 2 | 4.7.2 | Window Handle Installation + Adjustment | 1 | MYA | B | 16 | 0 | 16 | 2 | 6 | 12 | 12 | 0 | 2026-04-20 | 5 | 2026-04-24 | 0% | 0 | 0% | 0% | 0 |  | 2026-04-20: 2; 2026-04-21: 2; 2026-04-22: 2; 2026-04-23: 2; 2026-04-24: 2; 2026-04-25: 2
4 | 7 | 3 | 4.7.3 | Paint - Touch up | 1 | MYA | A | 107 | 0 | 107 | 2 | 24 | 48 | 48 | 0 | 2026-03-30 | 20 | 2026-04-24 | 0% | 0 | 0% | 0% | 0 |  | 2026-03-30: 2; 2026-03-31: 2; 2026-04-01: 2; 2026-04-02: 2; 2026-04-03: 2; 2026-04-04: 2; 2026-04-06: 2; 2026-04-07: 2; 2026-04-08: 2; 2026-04-09: 2; 2026-04-10: 2; 2026-04-11: 2; 2026-04-13: 2; 2026-04-14: 2; 2026-04-15: 2; 2026-04-16: 2; 2026-04-17: 2; 2026-04-18: 2; 2026-04-20: 2; 2026-04-21: 2; 2026-04-22: 2; 2026-04-23: 2; 2026-04-24: 2; 2026-04-25: 2
4 | 8 | 0 | 4.8.0 | WT-1.6 | [8 empty] | 8 | [5 empty] | 0% | 0 | 0% | 0% | 0
4 | 8 | 1 | 4.8.1 | Membrane Control + Rectafication | 1 | MYA | A | 2 | 0 | 2 | 2 | 4 | 8 | 8 | 0 | 2026-04-06 | 4 | 2026-04-09 | 0% | 0 | 0% | 0% | 0 |  | 2026-04-06: 2; 2026-04-07: 2; 2026-04-08: 2; 2026-04-09: 2
4 | 9 | 0 | 4.9.0 | FT-06 Pool facade | [8 empty] | 76 | [5 empty] | 5.263% | 4 | 0% | 0% | 0
4 | 9 | 1 | 4.9.1 | Mock-up on Site | 1.5 | MYA |  | 1 | 1 | 0 | 2 | 2 | 4 | 4 | 0 | 2025-11-26 | 2 | 2025-11-27 | 100% | 4 | 0% | 100% | 4 |  | 2025-11-26: 2; 2025-11-27: 2
4 | 9 | 2 | 4.9.2 | Approval by SOB/DSI/URW |  | URW | [13 empty] | 0 |  |  | 0
4 | 9 | 3 | 4.9.3 | Procurement + Manufacturing |  | MYA |  | 18 | 0 | 18 | [8 empty] | 0% | 0 |  |  | 0
4 | 9 | 4 | 4.9.4 | Installation | 1.5 | MYA | A | 18 | 0 | 18 | 4 | 18 | 72 | 72 | 0 | 2026-04-06 | 11 | 2026-04-20 | 0% | 0 | 0% | 0% | 0 |  | 2026-04-06: 2; 2026-04-07: 2; 2026-04-08: 2; 2026-04-09: 2; 2026-04-10: 2; 2026-04-11: 2; 2026-04-13: 2; 2026-04-14: 2; 2026-04-15: 2; 2026-04-16: 2; 2026-04-17: 2; 2026-04-18: 2; 2026-04-20: 6; 2026-04-21: 6; 2026-04-22: 6; 2026-04-23: 10; 2026-04-24: 10; 2026-04-25: 10
4 | 10 | 0 | 4.10.0 | FT03 Acoustic Reinforcement | [8 empty] | 42 | [5 empty] | 9.524% | 4 | 0% | 0% | 0
4 | 10 | 1 | 4.10.1 | Mock-up on Site | 1.5 | MYA |  | 1 | 1 | 0 | 2 | 2 | 4 | 4 | 0 | 2025-11-28 | 1 | 2025-11-28 | 100% | 4 | 0% | 100% | 4 |  | 2025-11-28: 2; 2025-11-29: 2
4 | 10 | 2 | 4.10.2 | Acoustic Testing |  | MYA |  | 1 | 0 | 1 | 2 | 1 | 2 | 0 | 2 |  |  |  | 0% | 0 | 0% | 0% | 0
4 | 10 | 3 | 4.10.3 | Approval by SOB/DSI/URW |  | URW | [13 empty] | 0 |  |  | 0
4 | 10 | 4 | 4.10.4 | Procurement + Manufacturing |  | MYA |  | 20 | 0 | 20 |  |  |  | 0 | 0 |  |  |  | 0% | 0 |  |  | 0
4 | 10 | 5 | 4.10.5 | Installation | 1.5 | MYA | A | 20 | 0 | 20 | 2 | 18 | 36 | 36 | 0 | 2026-04-27 | 5 | 2026-05-01 | 0% | 0 | 0% | 0% | 0 |  | 2026-04-27: 6; 2026-04-28: 6; 2026-04-29: 6; 2026-04-30: 6; 2026-05-01: 6; 2026-05-02: 6
4 | 11 | 0 | 4.11.0 | Documentation + Testing
4 | 11 | 1 | 4.11.1 | WT04 |  | MYA
4 | 11 | 2 | 4.11.2 | WT01.5 |  | MYA
4 | 11 | 3 | 4.11.3 | FT15 |  | MYA
4 | 11 | 4 | 4.11.4 | FT03 |  | MYA
4 | 11 | 5 | 4.11.5 | FT06 |  | MYA
4 | 11 | 6 | 4.11.6 | FT09 |  | MYA
4 | 11 | 7 | 4.11.7 | FT14 |  | MYA
4 | 12 | 0 | 4.12.0 | Warehouse + Supervisor | [20 empty] | 2025-11-24: 3; 2025-11-25: 3; 2025-11-26: 3; 2025-11-27: 3; 2025-11-28: 3; 2025-11-29: 3; 2025-12-01: 2; 2025-12-02: 2; 2025-12-03: 2; 2025-12-04: 2; 2025-12-05: 2; 2025-12-06: 2; 2025-12-08: 2; 2025-12-09: 2; 2025-12-10: 2; 2025-12-11: 2; 2025-12-12: 2; 2025-12-13: 2; 2025-12-15: 2; 2025-12-16: 2; 2025-12-17: 2; 2025-12-18: 2; 2025-12-19: 2; 2025-12-20: 2; 2025-12-22: 2; 2025-12-23: 2; 2025-12-24: 2; 2025-12-25: 2; 2025-12-26: 2; 2025-12-27: 2; 2025-12-29: 2; 2025-12-30: 2; 2025-12-31: 2; 2026-01-01: 2; 2026-01-02: 2; 2026-01-03: 2; 2026-01-05: 2; 2026-01-06: 2; 2026-01-07: 2; 2026-01-08: 2; 2026-01-09: 2; 2026-01-10: 2; 2026-01-12: 2; 2026-01-13: 2; 2026-01-14: 2; 2026-01-15: 2; 2026-01-16: 2; 2026-01-17: 2; 2026-01-19: 2; 2026-01-20: 2; 2026-01-21: 2; 2026-01-22: 2; 2026-01-23: 2; 2026-01-24: 2; 2026-01-26: 2; 2026-01-27: 2; 2026-01-28: 2; 2026-01-29: 2; 2026-01-30: 2; 2026-01-31: 2; 2026-02-02: 2; 2026-02-03: 2; 2026-02-04: 2; 2026-02-05: 2; 2026-02-06: 2; 2026-02-07: 2; 2026-02-09: 2; 2026-02-10: 2; 2026-02-11: 2; 2026-02-12: 2; 2026-02-13: 2; 2026-02-14: 2; 2026-02-16: 2; 2026-02-17: 2; 2026-02-18: 2; 2026-02-19: 2; 2026-02-20: 2; 2026-02-21: 2; 2026-02-23: 2; 2026-02-24: 2; 2026-02-25: 2; 2026-02-26: 2; 2026-02-27: 2; 2026-02-28: 2; 2026-03-02: 2; 2026-03-03: 2; 2026-03-04: 2; 2026-03-05: 2; 2026-03-06: 2; 2026-03-07: 2; 2026-03-09: 2; 2026-03-10: 2; 2026-03-11: 2; 2026-03-12: 2; 2026-03-13: 2; 2026-03-14: 2; 2026-03-16: 2; 2026-03-17: 2; 2026-03-18: 2; 2026-03-19: 2; 2026-03-20: 2; 2026-03-21: 2; 2026-03-23: 2; 2026-03-24: 2; 2026-03-25: 2; 2026-03-26: 2; 2026-03-27: 2; 2026-03-28: 2; 2026-03-30: 2; 2026-03-31: 2; 2026-04-01: 2; 2026-04-02: 2; 2026-04-03: 2; 2026-04-04: 2; 2026-04-06: 2; 2026-04-07: 2; 2026-04-08: 2; 2026-04-09: 2; 2026-04-10: 2; 2026-04-11: 2; 2026-04-13: 2; 2026-04-14: 2; 2026-04-15: 2; 2026-04-16: 2; 2026-04-17: 2; 2026-04-18: 2; 2026-04-20: 2; 2026-04-21: 2; 2026-04-22: 2; 2026-04-23: 2; 2026-04-24: 2; 2026-04-25: 2; 2026-04-27: 2; 2026-04-28: 2; 2026-04-29: 2; 2026-04-30: 2; 2026-05-01: 2; 2026-05-02: 2; 2026-05-04: 2; 2026-05-05: 2; 2026-05-06: 2; 2026-05-07: 2; 2026-05-08: 2; 2026-05-09: 2; 2026-05-11: 2; 2026-05-12: 2; 2026-05-13: 2; 2026-05-14: 2; 2026-05-15: 2; 2026-05-16: 2; 2026-05-18: 2; 2026-05-19: 2; 2026-05-20: 2; 2026-05-21: 2; 2026-05-22: 2; 2026-05-23: 2; 2026-05-25: 2; 2026-05-26: 2; 2026-05-27: 2; 2026-05-28: 2; 2026-05-29: 2; 2026-05-30: 2

## 260113_E2NS Terminplan
[24 empty] | 2025-10-01 | November 25 | [6 empty] | December 25 | [6 empty] | December 25 | [6 empty] | December 25 | [6 empty] | December 25 | [6 empty] | January 26 | [6 empty] | January 26 | [6 empty] | January 26 | [6 empty] | January 26 | [6 empty] | January 26 | [6 empty] | February 26 | [6 empty] | February 26 | [6 empty] | February 26 | [6 empty] | February 26 | [6 empty] | March 26 | [6 empty] | March 26 | [6 empty] | March 26 | [6 empty] | March 26 | [6 empty] | April 26 | [6 empty] | April 26 | [6 empty] | April 26 | [6 empty] | April 26 | [6 empty] | May 26 | [6 empty] | May 26 | [6 empty] | May 26 | [6 empty] | May 26 | [6 empty] | May 26 | [6 empty] | June 26 | [6 empty] | June 26 | [6 empty] | June 26 | [6 empty] | June 26 | [6 empty] | July 26 | [6 empty] | July 26 | [6 empty] | July 26 | [6 empty] | July 26 | [6 empty] | August 26 | [6 empty] | August 26 | [6 empty] | August 26 | [6 empty] | August 26 | [6 empty] | August 26 | [6 empty] | September 26 | [6 empty] | September 26 | [6 empty] | September 26 | [6 empty] | September 26 | [6 empty] | October 26 | [6 empty] | October 26 | [6 empty] | October 26 | [6 empty] | October 26 | [6 empty] | October 26 | [6 empty] | November 26 | [6 empty] | November 26 | [6 empty] | November 26
[16 empty] | E2NS | [8 empty] | 48 | [6 empty] | 49 | [6 empty] | 50 | [6 empty] | 51 | [6 empty] | 52 | [6 empty] | 1 | [6 empty] | 2 | [6 empty] | 3 | [6 empty] | 4 | [6 empty] | 5 | [6 empty] | 6 | [6 empty] | 7 | [6 empty] | 8 | [6 empty] | 9 | [6 empty] | 10 | [6 empty] | 11 | [6 empty] | 12 | [6 empty] | 13 | [6 empty] | 14 | [6 empty] | 15 | [6 empty] | 16 | [6 empty] | 17 | [6 empty] | 18 | [6 empty] | 19 | [6 empty] | 20 | [6 empty] | 21 | [6 empty] | 22 | [6 empty] | 23 | [6 empty] | 24 | [6 empty] | 25 | [6 empty] | 26 | [6 empty] | 27 | [6 empty] | 28 | [6 empty] | 29 | [6 empty] | 30 | [6 empty] | 31 | [6 empty] | 32 | [6 empty] | 33 | [6 empty] | 34 | [6 empty] | 35 | [6 empty] | 36 | [6 empty] | 37 | [6 empty] | 38 | [6 empty] | 39 | [6 empty] | 40 | [6 empty] | 41 | [6 empty] | 42 | [6 empty] | 43 | [6 empty] | 44 | [6 empty] | 45 | [6 empty] | 46 | [6 empty] | 47
[25 empty] | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 129 | 130 | 131 | 132 | 133 | 134 | 135 | 136 | 137 | 138 | 139 | 140 | 141 | 142 | 143 | 144 | 145 | 146 | 147 | 148 | 149 |  | 151 | 152 | 153 | 154 | 155 | 156 | 157 | 158 | 159 | 160 | 161 | 162 | 163 | 164 | 165 | 166 | 167 | 168 | 169 | 170 | 171 | 172 | 173 | 174 | 175 | 176 | 177 | 178 | 179 | 180 | 181 | 182 | 183 | 184 | 185 | 186 | 187 | 188 | 189 | 190 | 191 | 192 | 193 | 194 | 195 | 196 | 197 | 198 | 199 | 200 | 201 | 202 | 203 | 204 | 205 | 206 | 207 | 208 | 209 | 210 | 211 | 212 | 213 | 214 | 215 | 216 | 217 | 218 | 219 | 220 | 221 | 222 | 223 | 224 | 225 | 226 | 227 | 228 | 229 | 230 | 231 | 232 | 233 | 234 | 235 | 236 | 237 | 238 | 239 | 240 | 241 | 242 | 243 | 244 | 245 | 246 | 247 | 248 | 249 | 250 | 251 | 252 | 253 | 254 | 255 | 256 | 257 | 258 | 259 | 260 | 261 | 262 | 263 | 264 | 265 | 266 | 267 | 268 | 269 | 270 | 271 | 272 | 273 | 274 | 275 | 276 | 277 | 278 | 279 | 280 | 281 | 282 | 283 | 284 | 285 | 286 | 287 | 288 | 289 | 290 | 291 | 292 | 293 | 294 | 295 | 296 | 297 | 298 | 299 | 300 | 301 | 302 | 303 | 304 | 305 | 306 | 307 | 308 | 309 | 310 | 311 | 312 | 313 | 314 | 315 | 316 | 317 | 318 | 319 | 320 | 321 | 322 | 323 | 324 | 325 | 326 | 327 | 328 | 329 | 330 | 331 | 332 | 333 | 334 | 335 | 336 | 337 | 338 | 339 | 340 | 341 | 342 | 343 | 344 | 345 | 346 | 347 | 348 | 349 | 350 | 351 | 352 | 353 | 354 | 355 | 356 | 357 | 358 | 359 | 360 | 361 | 362 | 363 | 364 | 365 | 366 | 367 | 368 | 369 | 370 | 371 | 372 | 373 | 374 | 375 | 376 | 377 | 378 | 379 | 380 | 381 | 382 | 383 | 384 | 385 | 386 | 387 | 388 | 389 | 390 | 391 | 392 | 393 | 394 | 395 | 396 | 397 | 398 | 399 | 400 | 401 | 402 | 403 | 404
[25 empty] | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun
[25 empty] | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 49 | 49 | 49 | 49 | 49 | 49 | 49 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 43 | 43 | 43 | 43 | 43 | 43 | 43 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 47 | 47 | 47 | 47 | 47 | 47 | 47
x | time axis 2025-11-24 to 2026-11-22
|  |  | Pos. | Aufgabe/Tätigkeit | Presequities | Responsible | Group | QTY | Done | Rem. | Manpower | Duration | Total Manday |  |  | Beginn [Datum] | Ende nach [AT] | Ende [Datum] | Status |  | KW2 Progress | Cumulative Progress =<KW2 |  | Anmerkungen | bar: 2025-11-30; 2025-12-05 to 2025-12-07; 2025-12-14; 2025-12-19 to 2025-12-21
[13 empty] | 4169 | [5 empty] | 8.848% |  | 2026-01-11 |  |  |  | 2025-11-24: 15; 2025-11-25: 13; 2025-11-26: 15; 2025-11-27: 15; 2025-11-28: 15; 2025-11-29: 15; 2025-11-30: 0; 2025-12-01: 19; 2025-12-02: 19; 2025-12-03: 19; 2025-12-04: 19; 2025-12-05: 19; 2025-12-06: 19; 2025-12-07: 0; 2025-12-08: 13; 2025-12-09: 13; 2025-12-10: 13; 2025-12-11: 17; 2025-12-12: 17; 2025-12-13: 13; 2025-12-14: 0; 2025-12-15: 13; 2025-12-16: 13; 2025-12-17: 13; 2025-12-18: 13; 2025-12-19: 11; 2025-12-20: 2; 2025-12-21: 0; 2025-12-22: 2; 2025-12-23: 2; 2025-12-24: 2; 2025-12-25: 2; 2025-12-26: 2; 2025-12-27: 2; 2025-12-28: 0; 2025-12-29: 2; 2025-12-30: 2; 2025-12-31: 2; 2026-01-01: 2; 2026-01-02: 2; 2026-01-03: 2; 2026-01-04: 0; 2026-01-05: 2; 2026-01-06: 2; 2026-01-07: 2; 2026-01-08: 2; 2026-01-09: 2; 2026-01-10: 2; 2026-01-11: 0; 2026-01-12: 20; 2026-01-13: 20; 2026-01-14: 20; 2026-01-15: 20; 2026-01-16: 20; 2026-01-17: 20; 2026-01-18: 0; 2026-01-19: 20; 2026-01-20: 20; 2026-01-21: 20; 2026-01-22: 20; 2026-01-23: 20; 2026-01-24: 20; 2026-01-25: 0; 2026-01-26: 20; 2026-01-27: 20; 2026-01-28: 20; 2026-01-29: 20; 2026-01-30: 20; 2026-01-31: 20; 2026-02-01: 0; 2026-02-02: 46; 2026-02-03: 46; 2026-02-04: 46; 2026-02-05: 46; 2026-02-06: 46; 2026-02-07: 46; 2026-02-08: 0; 2026-02-09: 45; 2026-02-10: 45; 2026-02-11: 45; 2026-02-12: 45; 2026-02-13: 45; 2026-02-14: 45; 2026-02-15: 0; 2026-02-16: 43; 2026-02-17: 43; 2026-02-18: 43; 2026-02-19: 43; 2026-02-20: 43; 2026-02-21: 43; 2026-02-22: 0; 2026-02-23: 43; 2026-02-24: 43; 2026-02-25: 43; 2026-02-26: 43; 2026-02-27: 43; 2026-02-28: 37; 2026-03-01: 0; 2026-03-02: 51; 2026-03-03: 51; 2026-03-04: 51; 2026-03-05: 51; 2026-03-06: 51; 2026-03-07: 51; 2026-03-08: 0; 2026-03-09: 46; 2026-03-10: 46; 2026-03-11: 46; 2026-03-12: 46; 2026-03-13: 46; 2026-03-14: 46; 2026-03-15: 0; 2026-03-16: 51; 2026-03-17: 51; 2026-03-18: 51; 2026-03-19: 55; 2026-03-20: 55; 2026-03-21: 55; 2026-03-22: 0; 2026-03-23: 61; 2026-03-24: 61; 2026-03-25: 61; 2026-03-26: 61; 2026-03-27: 61; 2026-03-28: 61; 2026-03-29: 0; 2026-03-30: 48; 2026-03-31: 48; 2026-04-01: 48; 2026-04-02: 48; 2026-04-03: 45; 2026-04-04: 45; 2026-04-05: 0; 2026-04-06: 34; 2026-04-07: 34; 2026-04-08: 34; 2026-04-09: 34; 2026-04-10: 32; 2026-04-11: 32; 2026-04-12: 0; 2026-04-13: 38; 2026-04-14: 38; 2026-04-15: 38; 2026-04-16: 38; 2026-04-17: 38; 2026-04-18: 34; 2026-04-19: 0; 2026-04-20: 34; 2026-04-21: 34; 2026-04-22: 34; 2026-04-23: 34; 2026-04-24: 34; 2026-04-25: 34; 2026-04-26: 0; 2026-04-27: 16; 2026-04-28: 16; 2026-04-29: 16; 2026-04-30: 16; 2026-05-01: 16; 2026-05-02: 16; 2026-05-03: 0; 2026-05-04: 14; 2026-05-05: 14; 2026-05-06: 14; 2026-05-07: 14; 2026-05-08: 14; 2026-05-09: 14; 2026-05-10: 0; 2026-05-11: 14; 2026-05-12: 14; 2026-05-13: 14; 2026-05-14: 14; 2026-05-15: 14; 2026-05-16: 14; 2026-05-17: 0; 2026-05-18: 12; 2026-05-19: 12; 2026-05-20: 12; 2026-05-21: 12; 2026-05-22: 12; 2026-05-23: 12; 2026-05-24: 0; 2026-05-25: 12; 2026-05-26: 12; 2026-05-27: 12; 2026-05-28: 12; 2026-05-29: 12; 2026-05-30: 12; 2026-05-31: 0
[74 empty] | 20 | 20 | 20 | 20 | 20 | 20 |  | 20 | 20 | 20 | 20 | 20 | 20 |  | 20 | 20 | 20 | 20 | 20 | 20 |  | 26 | 26 | 26 | 26 | 26 | 26 |  | 25 | 25 | 25 | 25 | 25 | 25 |  | 23 | 23 | 23 | 23 | 23 | 23 |  | 23 | 23 | 23 | 23 | 23 | 17 |  | 31 | 31 | 31 | 31 | 31 | 31 |  | 26 | 26 | 26 | 26 | 26 | 26 |  | 31 | 31 | 31 | 35 | 35 | 35 |  | 41 | 41 | 41 | 41 | 41 | 41 |  | 48 | 48 | 48 | 48 | 45 | 45
1 | 0 | 0 | 1.0.0 | E2 N | [8 empty] | 1610 |  |  |  |  | 2026-04-03 | 12.68% | 204.1889 | 2 |  | 48
1 | 1 | 0 | 1.1.0 | E2N Outside Windows | [8 empty] | 540 | [5 empty] | 2.374% | 12.8205 |  |  | 0
1 | 1 | 1 | 1.1.1 | Dismantling of Drywall + Al Sheet | 1 | MYA | A | 156 | 8 | 148 | 2 | 125 | 250 | 250 | 0 | 2026-01-12 | 30 | 2026-02-20 | 5.128% | 12.8205 | 0% | 0% | 0 |  | 2026-01-12: 4; 2026-01-13: 4; 2026-01-14: 4; 2026-01-15: 4; 2026-01-16: 4; 2026-01-17: 4; 2026-01-19: 12; 2026-01-20: 12; 2026-01-21: 12; 2026-01-22: 12; 2026-01-23: 12; 2026-01-24: 12; 2026-01-26: 8; 2026-01-27: 8; 2026-01-28: 8; 2026-01-29: 8; 2026-01-30: 8; 2026-01-31: 8; 2026-02-02: 8; 2026-02-03: 8; 2026-02-04: 8; 2026-02-05: 8; 2026-02-06: 8; 2026-02-07: 8; 2026-02-09: 6; 2026-02-10: 6; 2026-02-11: 6; 2026-02-12: 6; 2026-02-13: 6; 2026-02-14: 6; 2026-02-16: 4; 2026-02-17: 4; 2026-02-18: 4; 2026-02-19: 4; 2026-02-20: 4; 2026-02-21: 2
1 | 1 | 2 | 1.1.2 | Application of New Membrane | 1 | MYA | A | 156 | 0 | 156 | 2 | 80 | 160 | 160 | 0 | 2026-01-19 | 30 | 2026-02-27 | 0% | 0 | 0% | 0% | 0 |  | 2026-01-19: 5; 2026-01-20: 5; 2026-01-21: 5; 2026-01-22: 5; 2026-01-23: 5; 2026-01-24: 5; 2026-01-26: 6; 2026-01-27: 6; 2026-01-28: 6; 2026-01-29: 6; 2026-01-30: 6; 2026-01-31: 6; 2026-02-02: 4; 2026-02-03: 4; 2026-02-04: 4; 2026-02-05: 4; 2026-02-06: 4; 2026-02-07: 4; 2026-02-09: 4; 2026-02-10: 4; 2026-02-11: 4; 2026-02-12: 4; 2026-02-13: 4; 2026-02-14: 4; 2026-02-16: 4; 2026-02-17: 4; 2026-02-18: 4; 2026-02-19: 4; 2026-02-20: 4; 2026-02-21: 6; 2026-02-23: 4; 2026-02-24: 4; 2026-02-25: 4; 2026-02-26: 4; 2026-02-27: 4
1 | 1 | 3 | 1.1.3 | Installation of Al. Sheet | 1 | MYA | A | 156 | 0 | 156 | 2 | 65 | 130 | 130 | 0 | 2026-01-26 | 25 | 2026-02-27 | 0% | 0 | 0% | 0% | 0 |  | 2026-01-26: 4; 2026-01-27: 4; 2026-01-28: 4; 2026-01-29: 4; 2026-01-30: 4; 2026-01-31: 4; 2026-02-02: 6; 2026-02-03: 6; 2026-02-04: 6; 2026-02-05: 6; 2026-02-06: 6; 2026-02-07: 6; 2026-02-09: 4; 2026-02-10: 4; 2026-02-11: 4; 2026-02-12: 4; 2026-02-13: 4; 2026-02-14: 4; 2026-02-16: 4; 2026-02-17: 4; 2026-02-18: 4; 2026-02-19: 4; 2026-02-20: 4; 2026-02-21: 4; 2026-02-23: 4; 2026-02-24: 4; 2026-02-25: 4; 2026-02-26: 4; 2026-02-27: 4; 2026-02-28: 2
1 | 1 | 4 | 1.1.4 | Installation of New Drywall | 1 | XXX | A | 156 | 0 | 156 |  |  | 0 | 0 | 0 |  |  |  | 0% | 0 |  |  | 0
1 | 2 | 0 | 1.2.0 | E2N Courtyard Windows | [8 empty] | 160 | [5 empty] | 79.61% | 127.3684 |  |  | 0
1 | 2 | 1 | 1.2.1 | Dismantling of Drywall | 1 | MYA | A | 76 | 76 | 0 | 10 | 8 | 80 | 80 | 0 | 2025-11-24 | 20 | 2025-12-19 | 100% | 80 | 0% | 100% | 80 |  | 2025-11-24: 2; 2025-11-25: 3; 2025-11-26: 3; 2025-11-27: 2; 2025-11-28: 2; 2025-11-29: 2; 2025-12-01: 4; 2025-12-02: 4; 2025-12-03: 4; 2025-12-04: 4; 2025-12-05: 4; 2025-12-06: 4; 2025-12-08: 4; 2025-12-09: 4; 2025-12-10: 4; 2025-12-11: 4; 2025-12-12: 4; 2025-12-13: 4; 2025-12-15: 4; 2025-12-16: 4; 2025-12-17: 4; 2025-12-18: 4; 2025-12-19: 2
1 | 2 | 2 | 1.2.2 | Application of New Membrane | 1 | MYA | A | 76 | 45 | 31 | 10 | 8 | 80 | 134 | -54 | 2025-12-08 | 35 | 2026-01-23 | 59.21% | 47.3684 | 0% | 55% | 44 |  | 2025-12-08: 4; 2025-12-09: 4; 2025-12-10: 4; 2025-12-11: 4; 2025-12-12: 4; 2025-12-13: 4; 2025-12-15: 4; 2025-12-16: 4; 2025-12-17: 4; 2025-12-18: 4; 2025-12-19: 4; 2026-01-12: 14; 2026-01-13: 14; 2026-01-14: 14; 2026-01-15: 14; 2026-01-16: 14; 2026-01-17: 14; 2026-01-19: 1; 2026-01-20: 1; 2026-01-21: 1; 2026-01-22: 1; 2026-01-23: 1; 2026-01-24: 1
1 | 2 | 3 | 1.2.3 | Installation of New Drywall | 1 | XXX | A | 76 | 0 | 76 |  |  | 0 | 0 | 0 |  |  |  | 0% | 0 |  |  | 0
1 | 3 | 0 | 1.3.0 | Garage entrance aluminum cladding (north) |  | MYA | B | 1 | 1 | 0 | 4 | 6 | 24 |  |  | 2025-12-01 | 5 | 2025-12-05 | 100% | 24 | 0% | 100% | 24 |  | 2025-12-01: 4; 2025-12-02: 4; 2025-12-03: 4; 2025-12-04: 4; 2025-12-05: 4; 2025-12-06: 4
1 | 4 | 0 | 1.4.0 | Hörmann Door (West) | [8 empty] | 24 | [5 empty] | 66.67% | 16 | 0% | 0% | 0
1 | 4 | 1 | 1.4.1 | Steel structure | 2 | MYA | B | 1 | 1 | 0 | 4 | 4 | 16 | 0 | 16 |  |  |  | 100% | 16 | 0% | 0% | 0
1 | 4 | 2 | 1.4.2 | Door | 2 | MYA | B | 1 | 0 | 1 | 4 | 2 | 8 | 8 | 0 | 2025-12-11 | 2 | 2025-12-12 | 0% | 0 | 0% | 100% | 8 |  | 2025-12-11: 4; 2025-12-12: 4
1 | 5 | 0 | 1.5.0 | FT-07 Glass Rotation and Gasket replacement (East-West) | 2,3,4 | MYA | A | 7 | 0 | 7 | 3 | 6 | 18 | 18 | 0 | 2026-03-02 | 5 | 2026-03-06 | 0% | 0 | 0% | 0% | 0 |  | 2026-03-02: 3; 2026-03-03: 3; 2026-03-04: 3; 2026-03-05: 3; 2026-03-06: 3; 2026-03-07: 3
1 | 6 | 0 | 1.6.0 | Breuninger facade –Bottom Al. Finishing Reinforcement | 2 | MYA | A | 30 | 30 | 0 | 2 | 6 | 12 | 12 | 0 | 2025-12-01 | 5 | 2025-12-05 | 100% | 12 | 0% | 100% | 12 |  | 2025-12-01: 2; 2025-12-02: 2; 2025-12-03: 2; 2025-12-04: 2; 2025-12-05: 2; 2025-12-06: 2
1 | 7 | 0 | 1.7.0 | RT02 Additional Balustrade Module (NTA) | 2 | MYA | C | 2 | 0 | 2 | 4 | 3 | 12 | 12 | 0 | 2026-03-02 | 3 | 2026-03-04 | 0% | 0 | 0% | 0% | 0 |  | 2026-03-02: 4; 2026-03-03: 4; 2026-03-04: 4
1 | 8 | 0 | 1.8.0 | FT-13 Canopy – Anodized Al. Sheet Replacement + Cap Replacement | 2.3 | MYA | B | 60 | 0 | 60 | 4 | 6 | 24 | 24 | 0 | 2026-03-30 | 5 | 2026-04-03 | 0% | 0 | 0% | 0% | 0 |  | 2026-03-30: 4; 2026-03-31: 4; 2026-04-01: 4; 2026-04-02: 4; 2026-04-03: 4; 2026-04-04: 4
1 | 9 | 0 | 1.9.0 | E2N - E3 Attika Connection Detail (East+North) | 2 | MYA | B | 2 | 0 | 2 | 2 | 4 | 8 | 12 | -4 | 2026-03-05 | 2 | 2026-03-06 | 0% | 0 | 0% | 0% | 0 |  | 2026-03-05: 4; 2026-03-06: 4; 2026-03-07: 4
1 | 10 | 0 | 1.10.0 | E2N East Stone FT15 Connection Detail | 2 | MYA | A | 1 | 1 | 0 | 2 | 6 | 12 | 12 | 0 | 2025-12-01 | 5 | 2025-12-05 | 100% | 12 | 0% | 100% | 12 |  | 2025-12-01: 2; 2025-12-02: 2; 2025-12-03: 2; 2025-12-04: 2; 2025-12-05: 2; 2025-12-06: 2
1 | 11 | 0 | 1.11.0 | General – Glass replacement | 2,3,4 | MYA | B | 9 | 0 | 9 | 4 | 5 | 20 | 0 | 20 |  |  |  | 0% | 0 | 0% | 0% | 0
1 | 12 | 0 | 1.12.0 | FT-18 | [8 empty] | 504 | [5 empty] | 0% | 0 | 0% | 0% | 0
1 | 12 | 1 | 1.12.1 | Paint repair and bolt replacement | 2.5 | MYA | A | 1 | 0 | 1 | 10 | 48 | 480 | 480 | 0 | 2026-02-02 | 40 | 2026-03-27 | 0% | 0 | 0% | 0% | 0 |  | 2026-02-02: 10; 2026-02-03: 10; 2026-02-04: 10; 2026-02-05: 10; 2026-02-06: 10; 2026-02-07: 10; 2026-02-09: 10; 2026-02-10: 10; 2026-02-11: 10; 2026-02-12: 10; 2026-02-13: 10; 2026-02-14: 10; 2026-02-16: 10; 2026-02-17: 10; 2026-02-18: 10; 2026-02-19: 10; 2026-02-20: 10; 2026-02-21: 10; 2026-02-23: 10; 2026-02-24: 10; 2026-02-25: 10; 2026-02-26: 10; 2026-02-27: 10; 2026-02-28: 10; 2026-03-02: 10; 2026-03-03: 10; 2026-03-04: 10; 2026-03-05: 10; 2026-03-06: 10; 2026-03-07: 10; 2026-03-09: 10; 2026-03-10: 10; 2026-03-11: 10; 2026-03-12: 10; 2026-03-13: 10; 2026-03-14: 10; 2026-03-16: 10; 2026-03-17: 10; 2026-03-18: 10; 2026-03-19: 10; 2026-03-20: 10; 2026-03-21: 10; 2026-03-23: 10; 2026-03-24: 10; 2026-03-25: 10; 2026-03-26: 10; 2026-03-27: 10; 2026-03-28: 10
1 | 12 | 2 | 1.12.2 | 1141 Parcel / Passage and parapet installation (NTA) | 2,3,4,5 | MYA | B | 1 | 0 | 1 | 4 | 6 | 24 | 24 | 0 | 2026-03-23 | 5 | 2026-03-27 | 0% | 0 | 0% | 0% | 0 |  | 2026-03-23: 4; 2026-03-24: 4; 2026-03-25: 4; 2026-03-26: 4; 2026-03-27: 4; 2026-03-28: 4
1 | 13 | 0 | 1.13.0 | Acoustic Roof FT-18 (NTA) | [8 empty] | 252 | [5 empty] | 0% | 0 | 0% | 0% | 0
1 | 13 | 1 | 1.13.1 | Installed Steel Drilling + Paint Touch up | 2,3,4,5 | MYA | C | 1 | 0 | 1 | 4 | 18 | 72 | 72 | 0 | 2026-02-23 | 15 | 2026-03-13 | 0% | 0 | 0% | 0% | 0 |  | 2026-02-23: 4; 2026-02-24: 4; 2026-02-25: 4; 2026-02-26: 4; 2026-02-27: 4; 2026-02-28: 4; 2026-03-02: 4; 2026-03-03: 4; 2026-03-04: 4; 2026-03-05: 4; 2026-03-06: 4; 2026-03-07: 4; 2026-03-09: 4; 2026-03-10: 4; 2026-03-11: 4; 2026-03-12: 4; 2026-03-13: 4; 2026-03-14: 4
1 | 13 | 2 | 1.13.2 | Acoustic Roof Secondary Steel Installation | 2,3,4,5 | MYA | C | 1 | 0 | 1 | 4 | 18 | 72 | 72 | 0 | 2026-03-09 | 15 | 2026-03-27 | 0% | 0 | 0% | 0% | 0 |  | 2026-03-09: 4; 2026-03-10: 4; 2026-03-11: 4; 2026-03-12: 4; 2026-03-13: 4; 2026-03-14: 4; 2026-03-16: 4; 2026-03-17: 4; 2026-03-18: 4; 2026-03-19: 4; 2026-03-20: 4; 2026-03-21: 4; 2026-03-23: 4; 2026-03-24: 4; 2026-03-25: 4; 2026-03-26: 4; 2026-03-27: 4; 2026-03-28: 4
1 | 13 | 3 | 1.13.3 | Modül installation | 2,3,4,5 | MYA | C | 1 | 0 | 1 | 6 | 18 | 108 | 108 | 0 | 2026-03-16 | 15 | 2026-04-03 | 0% | 0 | 0% | 0% | 0 |  | 2026-03-16: 6; 2026-03-17: 6; 2026-03-18: 6; 2026-03-19: 6; 2026-03-20: 6; 2026-03-21: 6; 2026-03-23: 6; 2026-03-24: 6; 2026-03-25: 6; 2026-03-26: 6; 2026-03-27: 6; 2026-03-28: 6; 2026-03-30: 6; 2026-03-31: 6; 2026-04-01: 6; 2026-04-02: 6; 2026-04-03: 6; 2026-04-04: 6
1 | 14 | 0 | 1.14.0 | Documentation + Testing | [15 empty] | 0 |  |  | 0
1 | 14 | 1 | 1.14.1 | WT01 |  | MYA |  |  |  |  | 0 | 0 | 0 | [6 empty] | 0 |  |  | 0
1 | 14 | 2 | 1.14.2 | FT08 |  | MYA |  |  |  |  | 0 | 0 | 0 | [6 empty] | 0 |  |  | 0
1 | 14 | 3 | 1.14.3 | FT07 |  | MYA |  |  |  |  | 0 | 0 | 0 | [6 empty] | 0 |  |  | 0
[20 empty] | 0 |  |  | 0
2 | 0 | 0 | 2.0.0 | E2S Exterior | [8 empty] | 1101 |  |  |  |  | 2026-04-17 | 14.23% | 156.7035 |  |  | 12
2 | 1 | 0 | 2.1.0 | FT-02 Zigzak | [8 empty] | 15 | [5 empty] | 97.64% | 14.6464 | 0% | 0% | 0
2 | 1 | 1 | 2.1.1 | Zigzak Mängel (West) | 2.3 | MYA | A | 120 | 120 | 0 | 3 | 1 | 3 | 3 | 0 |  |  |  | 100% | 3 | 0% | 100% | 3 |  | 2025-11-24: 3
2 | 1 | 2 | 2.1.2 | Zigzak Mängel (South) | 2.3 | MYA | A | 80 | 77 | 3 | 2 | 3 | 6 | 0 | 6 |  |  |  | 96.25% | 5.775 | 0% | 0% | 0
2 | 1 | 3 | 2.1.3 | Zigzak Mängel (East) | 2.3 | MYA | A | 140 | 137 | 3 | 2 | 3 | 6 | 0 | 6 |  |  |  | 97.86% | 5.8714 | 0% | 0% | 0
2 | 2 | 0 | 2.2.0 | WT-1.5 | [8 empty] | 0 | [5 empty] | 100% | 0
2 | 2 | 1 | 2.2.1 | Mängel (Galvanized sheet end Membran) (West) | 2.3 | MYA | A | 45 | 45 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 100% | 0 |  |  | 0
2 | 3 | 0 | 2.3.0 | FT-05 | [8 empty] | 102 | [5 empty] | 35.29% | 36 | 0% | 0% | 0
2 | 3 | 1 | 2.3.1 | Glass installation | 2,3,4 | MYA | B | 5 | 0 | 5 | 4 | 3 | 12 | 12 | 0 | 2026-03-19 | 2 | 2026-03-20 | 0% | 0 | 0% | 0% | 0 |  | 2026-03-19: 4; 2026-03-20: 4; 2026-03-21: 4
2 | 3 | 2 | 2.3.2 | Membrane control (Big) | 2.3 | MYA | A | 6 | 0 | 6 | 3 | 30 | 90 | 90 | 0 | 2026-02-12 | 25 | 2026-03-18 | 0% | 0 | 0% | 0% | 0 |  | 2026-02-12: 3; 2026-02-13: 3; 2026-02-14: 3; 2026-02-16: 3; 2026-02-17: 3; 2026-02-18: 3; 2026-02-19: 3; 2026-02-20: 3; 2026-02-21: 3; 2026-02-23: 3; 2026-02-24: 3; 2026-02-25: 3; 2026-02-26: 3; 2026-02-27: 3; 2026-02-28: 3; 2026-03-02: 3; 2026-03-03: 3; 2026-03-04: 3; 2026-03-05: 3; 2026-03-06: 3; 2026-03-07: 3; 2026-03-09: 3; 2026-03-10: 3; 2026-03-11: 3; 2026-03-12: 3; 2026-03-13: 3; 2026-03-14: 3; 2026-03-16: 3; 2026-03-17: 3; 2026-03-18: 3
2 | 3 | 3 | 2.3.3 | Membrane control (Small) | 2.3 | MYA | A | 6 | 4 | 2 | 3 | 18 | 54 | 54 | 0 | 2025-11-24 | 58 | 2026-02-11 | 66.67% | 36 | 0% | 50% | 27 |  | 2025-11-24: 5; 2025-11-25: 5; 2025-11-26: 5; 2025-11-27: 4; 2025-11-28: 4; 2025-11-29: 4; 2026-02-02: 3; 2026-02-03: 3; 2026-02-04: 3; 2026-02-05: 3; 2026-02-06: 3; 2026-02-07: 3; 2026-02-09: 3; 2026-02-10: 3; 2026-02-11: 3
2 | 4 | 0 | 2.4.0 | Attika | [8 empty] | 102 | [5 empty] | 76.77% | 78.3037 | 0% | 0% | 0
2 | 4 | 1 | 2.4.1 | 7.OG | 2 | MYA | B | 200 | 191 | 9 | 5 | 3 | 15 | 15 | 0 | 2025-12-01 | 3 | 2025-12-03 | 95.5% | 14.325 | 0% | 100% | 15 |  | 2025-12-01: 5; 2025-12-02: 5; 2025-12-03: 5
2 | 4 | 2 | 2.4.2 | 5.OG | 2 | MYA | B | 24 | 23 | 1 | 5 | 3 | 15 | 15 | 0 | 2025-12-04 | 2 | 2025-12-05 | 95.83% | 14.375 | 0% | 100% | 15 |  | 2025-12-04: 5; 2025-12-05: 5; 2025-12-06: 5
2 | 4 | 3 | 2.4.3 | 3.OG | [8 empty] | 72 | 72 | 0 |  |  |  | 68.89% | 49.6037 | 0% | 0% | 0
2 | 4 | 4 | 2.4.3.1 | New Design - Coordination with Roofing (NTA) |  | MYA | [7 empty] | 0 | 0 |  |  |  |  | 0 |  |  | 0
2 | 4 | 5 | 2.4.3.2 | 3.OG Attika (West) | 2.3 | MYA | C | 28 | 16 | 12 | 3 | 12 | 36 | 36 | 0 | 2025-12-08 | 74 | 2026-03-19 | 57.14% | 20.5714 | 0% | 91.67% | 33 |  | 2025-12-08: 3; 2025-12-09: 3; 2025-12-10: 3; 2025-12-11: 3; 2025-12-12: 3; 2025-12-13: 3; 2025-12-15: 3; 2025-12-16: 3; 2025-12-17: 3; 2025-12-18: 3; 2025-12-19: 3; 2025-12-20: 0; 2026-03-19: 3
2 | 4 | 6 | 2.4.3.3 | 3.OG Attika (East) | 2.3 | MYA | C | 31 | 25 | 6 | 3 | 12 | 36 | 36 | 0 | 2026-01-12 | 59 | 2026-04-02 | 80.65% | 29.0323 | 0% | 0% | 0 |  | 2026-03-20: 3; 2026-03-21: 3; 2026-03-23: 3; 2026-03-24: 3; 2026-03-25: 3; 2026-03-26: 3; 2026-03-27: 3; 2026-03-28: 3; 2026-03-30: 3; 2026-03-31: 3; 2026-04-01: 3; 2026-04-02: 3
2 | 5 | 0 | 2.5.0 | Steel substructure for ceramic tile installation (NTA) |  | MYA | C | 2 | 2 | 0 | 4 | 4 | 16 |  |  | 2025-11-27 | 2 | 2025-11-28 | 100% | 16 | 0% | 75% | 12 |  | 2025-11-27: 4; 2025-11-28: 4; 2025-11-29: 4
2 | 6 | 0 | 2.6.0 | FT-12 - Canopy (Pullman) | [8 empty] | 132 | [5 empty] | 0% | 0 | 0% | 0% | 0
2 | 6 | 1 | 2.6.1 | Steel installation | 2,3,4 | MYA | B | 40 | 0 | 40 | 5 | 12 | 60 | 60 | 0 | 2026-03-02 | 10 | 2026-03-13 | 0% | 0 | 0% | 0% | 0 |  | 2026-03-02: 5; 2026-03-03: 5; 2026-03-04: 5; 2026-03-05: 5; 2026-03-06: 5; 2026-03-07: 5; 2026-03-09: 5; 2026-03-10: 5; 2026-03-11: 5; 2026-03-12: 5; 2026-03-13: 5; 2026-03-14: 5
2 | 6 | 2 | 2.6.2 | Aluminium Substructure | 2,3,4 | MYA | B | 105 | 0 | 105 | 4 | 12 | 48 | 48 | 0 | 2026-03-16 | 10 | 2026-03-27 | 0% | 0 | 0% | 0% | 0 |  | 2026-03-16: 4; 2026-03-17: 4; 2026-03-18: 4; 2026-03-19: 4; 2026-03-20: 4; 2026-03-21: 4; 2026-03-23: 4; 2026-03-24: 4; 2026-03-25: 4; 2026-03-26: 4; 2026-03-27: 4; 2026-03-28: 4
2 | 6 | 3 | 2.6.3 | Aluminium Cladding | 2,3,4 | MYA | B | 143 | 0 | 143 | 4 | 6 | 24 | 24 | 0 | 2026-03-23 | 5 | 2026-03-27 | 0% | 0 | 0% | 0% | 0 |  | 2026-03-23: 4; 2026-03-24: 4; 2026-03-25: 4; 2026-03-26: 4; 2026-03-27: 4; 2026-03-28: 4
2 | 7 | 0 | 2.7.0 | Dorma - Sliding door track installation (East) |  | MYA | B | 1 | 0 | 1 | 2 | 3 | 6 | [5 empty] | 0% | 0 | 0% | 0% | 0
2 | 8 | 0 | 2.8.0 | FT14 Additional Spandrel Panel (NTA) | [8 empty] | 10 | [5 empty] | 0% | 0 | 0% | 0% | 0
2 | 8 | 1 | 2.8.1 | New Design |  | MYA | [13 empty] | 0
2 | 8 | 2 | 2.8.2 | Approval by SOB / NTA Approval by URW |  | SOB | [13 empty] | 0
2 | 8 | 3 | 2.8.3 | Procurement + Manufacturing |  | MYA |  | 2 | 0 | 2 |  |  | 0 | [5 empty] | 0% | 0
2 | 8 | 4 | 2.8.4 | Installation | 1 | MYA | C | 2 | 0 | 2 | 2 | 5 | 10 | 10 | 0 | 2026-04-13 | 5 | 2026-04-17 | 0% | 0 | 0% | 0% | 0 |  | 2026-04-13: 2; 2026-04-14: 2; 2026-04-15: 2; 2026-04-16: 2; 2026-04-17: 2
2 | 9 | 0 | 2.9.0 | Additional Vent backside of Louver E2S West (NTA) | [8 empty] | 10 | [5 empty] | 0% | 0 | 0% | 0% | 0
2 | 9 | 1 | 2.9.1 | New Design |  | MYA | [13 empty] | 0 |  |  | 0
2 | 9 | 2 | 2.9.2 | Approval by SOB / NTA Approval by URW |  | SOB | [13 empty] | 0 |  |  | 0
2 | 9 | 3 | 2.9.3 | Procurement + Manufacturing |  | MYA |  | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  |  | 0% | 0 |  |  | 0
2 | 9 | 4 | 2.9.4 | Installation | 1.6 | MYA | C | 2 | 0 | 2 | 2 | 5 | 10 | 10 | 0 | 2026-04-13 | 5 | 2026-04-17 | 0% | 0 | 0% | 0% | 0 |  | 2026-04-13: 2; 2026-04-14: 2; 2026-04-15: 2; 2026-04-16: 2; 2026-04-17: 2
2 | 10 | 0 | 2.10.0 | General – Glass replacement |  | MYA | B | 36 | 0 | 36 | 4 | 12 | 48 | [5 empty] | 0% | 0 | 0% | 0% | 0
2 | 11 | 0 | 2.11.0 | Interkom Glasses (NTA) |  | MYA | C | 6 | 0 | 6 | 4 | 6 | 24 | [5 empty] | 0% | 0 | 0% | 0% | 0
2 | 12 | 0 | 2.12.0 | FT-18 | [8 empty] | 588 | [5 empty] | 1.999% | 11.7534 | 0% | 0% | 0
2 | 12 | 1 | 2.12.1 | Module Installation | 2.6 | MYA | B | 146 | 143 | 3 | 4 | 3 | 12 | 12 | 0 | 2026-03-26 | 2 | 2026-03-27 | 97.95% | 11.7534 | 0% | 0% | 0 |  | 2026-03-26: 4; 2026-03-27: 4; 2026-03-28: 4
2 | 12 | 2 | 2.12.2 | Paint repair and bolt replacement | 2.5 | MYA | A | 1 | 0 | 1 | 10 | 48 | 480 | 480 | 0 | 2026-02-02 | 40 | 2026-03-27 | 0% | 0 | 0% | 0% | 0 |  | 2026-02-02: 10; 2026-02-03: 10; 2026-02-04: 10; 2026-02-05: 10; 2026-02-06: 10; 2026-02-07: 10; 2026-02-09: 10; 2026-02-10: 10; 2026-02-11: 10; 2026-02-12: 10; 2026-02-13: 10; 2026-02-14: 10; 2026-02-16: 10; 2026-02-17: 10; 2026-02-18: 10; 2026-02-19: 10; 2026-02-20: 10; 2026-02-21: 10; 2026-02-23: 10; 2026-02-24: 10; 2026-02-25: 10; 2026-02-26: 10; 2026-02-27: 10; 2026-02-28: 10; 2026-03-02: 10; 2026-03-03: 10; 2026-03-04: 10; 2026-03-05: 10; 2026-03-06: 10; 2026-03-07: 10; 2026-03-09: 10; 2026-03-10: 10; 2026-03-11: 10; 2026-03-12: 10; 2026-03-13: 10; 2026-03-14: 10; 2026-03-16: 10; 2026-03-17: 10; 2026-03-18: 10; 2026-03-19: 10; 2026-03-20: 10; 2026-03-21: 10; 2026-03-23: 10; 2026-03-24: 10; 2026-03-25: 10; 2026-03-26: 10; 2026-03-27: 10; 2026-03-28: 10
2 | 12 | 3 | 2.12.3 | Trapezoidal sheet installation | 2.5 | MYA | B | 265 | 0 | 265 | 4 | 24 | 96 | 96 | 0 | 2026-03-16 | 10 | 2026-03-27 | 0% | 0 | 0% | 0% | 0 |  | 2026-03-16: 8; 2026-03-17: 8; 2026-03-18: 8; 2026-03-19: 8; 2026-03-20: 8; 2026-03-21: 8; 2026-03-23: 8; 2026-03-24: 8; 2026-03-25: 8; 2026-03-26: 8; 2026-03-27: 8; 2026-03-28: 8
2 | 13 | 0 | 2.13.0 | Doors | [8 empty] | 48 | [5 empty] | 0% | 0 | 0% | 0% | 0
2 | 13 | 1 | 2.13.1 | Terminal Doors | 2 | MYA | A | 12 | 0 | 12 | 4 | 12 | 48 | 0 | 48 |  |  |  | 0% | 0 | 0% | 0% | 0
2 | 13 | 2 | 2.13.2 | Hotel Doors | 2 | MYA | A | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  |  | 0% | 0 |  |  | 0
[20 empty] | 0 |  |  | 0
3 | 0 | 0 | 3.0.0 | E2S Inenhof | [8 empty] | 936 |  |  |  |  | 2026-05-29 | 0% | 0 |  |  | 0
3 | 1 | 0 | 3.1.0 | WT-04 | [8 empty] | 108 | [5 empty] | 0% | 0 | 0% | 0% | 0
3 | 1 | 1 | 3.1.1 | Schüco adaptör profile | 2.6 | MYA | A | 62 | 0 | 62 | 2 | 18 | 36 | 36 | 0 | 2026-02-16 | 15 | 2026-03-06 | 0% | 0 | 0% | 0% | 0 |  | 2026-02-16: 2; 2026-02-17: 2; 2026-02-18: 2; 2026-02-19: 2; 2026-02-20: 2; 2026-02-21: 2; 2026-02-23: 2; 2026-02-24: 2; 2026-02-25: 2; 2026-02-26: 2; 2026-02-27: 2; 2026-02-28: 2; 2026-03-02: 2; 2026-03-03: 2; 2026-03-04: 2; 2026-03-05: 2; 2026-03-06: 2; 2026-03-07: 2
3 | 1 | 2 | 3.1.2 | Stone Installation | 2.6 | MYA | A | 53 | 0 | 53 | 4 | 6 | 24 | 24 | 0 | 2026-02-16 | 5 | 2026-02-20 | 0% | 0 | 0% | 0% | 0 |  | 2026-02-16: 4; 2026-02-17: 4; 2026-02-18: 4; 2026-02-19: 4; 2026-02-20: 4; 2026-02-21: 4
3 | 1 | 3 | 3.1.3 | Glass installation | 2.6 | MYA | A | 5 | 0 | 5 | 4 | 6 | 24 | 24 | 0 | 2026-02-23 | 5 | 2026-02-27 | 0% | 0 | 0% | 0% | 0 |  | 2026-02-23: 4; 2026-02-24: 4; 2026-02-25: 4; 2026-02-26: 4; 2026-02-27: 4; 2026-02-28: 4
3 | 1 | 4 | 3.1.4 | Cocoon-Coordination* Depending on them | 2.6 | MYA | A | 1 | 0 | 1 | 2 | 12 | 24 | 6 | 18 |  |  |  | 0% | 0 | 0% | 25% | 6 |  | 2025-11-24: 2; 2025-11-25: 2; 2025-11-26: 2
3 | 2 | 0 | 3.2.0 | WT-1.5 | [8 empty] | 12 | [5 empty] | 0% | 0 | 0% | 0% | 0
3 | 2 | 1 | 3.2.1 | Mängel (Galvanized sheet end Membran) (West) | 2.6 | MYA | A | 33 | 33 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 100% | 0 |  |  | 0
3 | 2 | 2 | 3.2.2 | Schüco adaptör profile | 2.6 | MYA | A | 18 | 0 | 18 | 2 | 6 | 12 | 12 | 0 | 2026-03-16 | 5 | 2026-03-20 | 0% | 0 | 0% | 0% | 0 |  | 2026-03-16: 2; 2026-03-17: 2; 2026-03-18: 2; 2026-03-19: 2; 2026-03-20: 2; 2026-03-21: 2
3 | 3 | 0 | 3.3.0 | FT-03 | [8 empty] | 186 | [5 empty] | 0% | 0 | 0% | 0% | 0
3 | 3 | 1 | 3.3.1 | Phonotherm structural board + Flashing Installation. | 2 | MYA | B | 107 | 0 | 107 | 2 | 18 | 36 | 36 | 0 | 2026-03-16 | 15 | 2026-04-03 | 0% | 0 | 0% | 0% | 0 |  | 2026-03-16: 2; 2026-03-17: 2; 2026-03-18: 2; 2026-03-19: 2; 2026-03-20: 2; 2026-03-21: 2; 2026-03-23: 2; 2026-03-24: 2; 2026-03-25: 2; 2026-03-26: 2; 2026-03-27: 2; 2026-03-28: 2; 2026-03-30: 2; 2026-03-31: 2; 2026-04-01: 2; 2026-04-02: 2; 2026-04-03: 2; 2026-04-04: 2
3 | 3 | 2 | 3.3.2 | Glass Installation - Pressure + Cover | 1,2,7,8 | MYA | B | 27 | 0 | 27 | 5 | 6 | 30 | 30 | 0 | 2026-03-30 | 5 | 2026-04-03 | 0% | 0 | 0% | 0% | 0 |  | 2026-03-30: 5; 2026-03-31: 5; 2026-04-01: 5; 2026-04-02: 5; 2026-04-03: 5; 2026-04-04: 5
3 | 3 | 3 | 3.3.3 | Aluminum sheet under the console end ceramic back, steel construction (East-West) | 2,6,7,8 | MYA | B | 38 | 0 | 38 | 4 | 24 | 96 | 96 | 0 | 2026-03-02 | 10 | 2026-03-13 | 0% | 0 | 0% | 0% | 0 |  | 2026-03-02: 8; 2026-03-03: 8; 2026-03-04: 8; 2026-03-05: 8; 2026-03-06: 8; 2026-03-07: 8; 2026-03-09: 8; 2026-03-10: 8; 2026-03-11: 8; 2026-03-12: 8; 2026-03-13: 8; 2026-03-14: 8
3 | 3 | 4 | 3.3.4 | Top Finish Attika (Anc+Const.+Membr+Sheet) (North) | 2 | MYA | B | 39 | 0 | 39 | 2 | 6 | 12 | 12 | 0 | 2026-03-23 | 8 | 2026-04-01 | 0% | 0 | 0% | 0% | 0 |  | 2026-03-23: 2; 2026-03-24: 2; 2026-03-25: 2; 2026-03-30: 2; 2026-03-31: 2; 2026-04-01: 2
3 | 3 | 5 | 3.3.5 | Installation of steel construction behind stone cladding (South) | 2.6 | MYA | B | 30 | 0 | 30 | 2 | 6 | 12 | 12 | 0 | 2026-03-23 | 8 | 2026-04-01 | 0% | 0 | 0% | 0% | 0 |  | 2026-03-23: 2; 2026-03-24: 2; 2026-03-25: 2; 2026-03-30: 2; 2026-03-31: 2; 2026-04-01: 2
3 | 4 | 0 | 3.4.0 | RT-01 Glass Balustrade | [8 empty] | 150 | [5 empty] | 0% | 0 | 0% | 0% | 0
3 | 4 | 1 | 3.4.1 | Brackets (NTA) | 2 | MYA | C | 173 | 0 | 173 | 3 | 18 | 54 | 54 | 0 | 2026-02-02 | 10 | 2026-02-13 | 0% | 0 | 0% | 0% | 0 |  | 2026-02-02: 3; 2026-02-03: 3; 2026-02-04: 3; 2026-02-05: 3; 2026-02-06: 3; 2026-02-07: 3; 2026-02-09: 6; 2026-02-10: 6; 2026-02-11: 6; 2026-02-12: 6; 2026-02-13: 6; 2026-02-14: 6
3 | 4 | 2 | 3.4.2 | Roofing Works |  | HOE | [7 empty] | 0 | 0 |  |  |  |  | 0 |  |  | 0
3 | 4 | 3 | 3.4.3 | Steel Construction | 2 | MYA | B | 173 | 0 | 173 | 2 | 6 | 12 | 12 | 0 | 2026-03-30 | 5 | 2026-04-03 | 0% | 0 | 0% | 0% | 0 |  | 2026-03-30: 2; 2026-03-31: 2; 2026-04-01: 2; 2026-04-02: 2; 2026-04-03: 2; 2026-04-04: 2
3 | 4 | 4 | 3.4.4 | Aluminum Module | 2 | MYA | B | 62 | 0 | 62 | 2 | 6 | 12 | 12 | 0 | 2026-03-30 | 5 | 2026-04-03 | 0% | 0 | 0% | 0% | 0 |  | 2026-03-30: 2; 2026-03-31: 2; 2026-04-01: 2; 2026-04-02: 2; 2026-04-03: 2; 2026-04-04: 2
3 | 4 | 5 | 3.4.5 | Attika Installation | 2 | MYA | B | 62 | 0 | 62 | 2 | 12 | 24 | 24 | 0 | 2026-04-02 | 5 | 2026-04-08 | 0% | 0 | 0% | 0% | 0 |  | 2026-04-02: 4; 2026-04-03: 4; 2026-04-04: 4; 2026-04-06: 4; 2026-04-07: 4; 2026-04-08: 4
3 | 4 | 6 | 3.4.6 | Glass installation | 2.8 | MYA | B | 103 | 0 | 103 | 4 | 12 | 48 | 48 | 0 | 2026-04-06 | 10 | 2026-04-17 | 0% | 0 | 0% | 0% | 0 |  | 2026-04-06: 4; 2026-04-07: 4; 2026-04-08: 4; 2026-04-09: 4; 2026-04-10: 4; 2026-04-11: 4; 2026-04-13: 4; 2026-04-14: 4; 2026-04-15: 4; 2026-04-16: 4; 2026-04-17: 4; 2026-04-18: 4
3 | 5 | 0 | 3.5.0 | FT16 A + B | [8 empty] | 168 | [5 empty] | 0% | 0 | 0% | 0% | 0
3 | 5 | 1 | 3.5.1 | Secondary Steel Construction (NTA) |  | MYA |  | 1 | 0 | 1 | [8 empty] | 0% | 0 |  |  | 0
3 | 5 | 2 | 3.5.2 | Design + Static Calculation |  | MYA |  | 1 | 0 | 1 | [8 empty] | 0% | 0 |  |  | 0
3 | 5 | 3 | 3.5.3 | Procurement + Manufacturing |  | MYA |  | 1 | 0 | 1 | [8 empty] | 0% | 0 |  |  | 0
3 | 5 | 4 | 3.5.4 | Installation | 2,6,8 | MYA | C | 1 | 0 | 1 | 4 | 12 | 48 | 48 | 0 | 2026-03-30 | 10 | 2026-04-10 | 0% | 0 | 0% | 0% | 0 |  | 2026-03-30: 4; 2026-03-31: 4; 2026-04-01: 4; 2026-04-02: 4; 2026-04-03: 4; 2026-04-04: 4; 2026-04-06: 4; 2026-04-07: 4; 2026-04-08: 4; 2026-04-09: 4; 2026-04-10: 4; 2026-04-11: 4
3 | 5 | 5 | 3.5.5 | Brackets | 2,6,8 | MYA | B | 162 | 0 | 162 | 4 | 12 | 48 | 48 | 0 | 2026-03-30 | 10 | 2026-04-10 | 0% | 0 | 0% | 0% | 0 |  | 2026-03-30: 4; 2026-03-31: 4; 2026-04-01: 4; 2026-04-02: 4; 2026-04-03: 4; 2026-04-04: 4; 2026-04-06: 4; 2026-04-07: 4; 2026-04-08: 4; 2026-04-09: 4; 2026-04-10: 4; 2026-04-11: 4
3 | 5 | 6 | 3.5.6 | Aluminium Profiles | 2,6,8 | MYA | B | 95 | 0 | 95 | 4 | 6 | 24 | 24 | 0 | 2026-04-06 | 5 | 2026-04-10 | 0% | 0 | 0% | 0% | 0 |  | 2026-04-06: 4; 2026-04-07: 4; 2026-04-08: 4; 2026-04-09: 4; 2026-04-10: 4; 2026-04-11: 4
3 | 5 | 7 | 3.5.7 | Aluminium Cladding | 2,6,8 | MYA | B | 121 | 0 | 121 | 4 | 12 | 48 | 48 | 0 | 2026-04-13 | 10 | 2026-04-24 | 0% | 0 | 0% | 0% | 0 |  | 2026-04-13: 4; 2026-04-14: 4; 2026-04-15: 4; 2026-04-16: 4; 2026-04-17: 4; 2026-04-18: 4; 2026-04-20: 4; 2026-04-21: 4; 2026-04-22: 4; 2026-04-23: 4; 2026-04-24: 4; 2026-04-25: 4
3 | 6 | 0 | 3.6.0 | FT17 | [8 empty] | 312 | [5 empty] | 0% | 0 | 0% | 0% | 0
3 | 6 | 1 | 3.6.1 | MEP + Other Works Completion |  | URW | [13 empty] | 0 |  |  | 0
3 | 6 | 2 | 3.6.2 | Brackets | 2,6,8 | MYA | B | 1673 | 0 | 1673 | 4 | 30 | 120 | 120 | 0 | 2026-04-27 | 15 | 2026-05-15 | 0% | 0 | 0% | 0% | 0 |  | 2026-04-27: 8; 2026-04-28: 8; 2026-04-29: 8; 2026-04-30: 8; 2026-05-01: 8; 2026-05-02: 8; 2026-05-04: 8; 2026-05-05: 8; 2026-05-06: 8; 2026-05-07: 8; 2026-05-08: 8; 2026-05-09: 8; 2026-05-11: 4; 2026-05-12: 4; 2026-05-13: 4; 2026-05-14: 4; 2026-05-15: 4; 2026-05-16: 4
3 | 6 | 3 | 3.6.3 | Aluminium Profiles | 2,6,8 | MYA | B | 1245 | 0 | 1245 | 4 | 12 | 48 | 48 | 0 | 2026-05-04 | 10 | 2026-05-15 | 0% | 0 | 0% | 0% | 0 |  | 2026-05-04: 4; 2026-05-05: 4; 2026-05-06: 4; 2026-05-07: 4; 2026-05-08: 4; 2026-05-09: 4; 2026-05-11: 4; 2026-05-12: 4; 2026-05-13: 4; 2026-05-14: 4; 2026-05-15: 4; 2026-05-16: 4
3 | 6 | 4 | 3.6.4 | Aluminium Cladding | 2,6,8 | MYA | B | 493 | 0 | 493 | 4 | 36 | 144 | 144 | 0 | 2026-05-11 | 15 | 2026-05-29 | 0% | 0 | 0% | 0% | 0 |  | 2026-05-11: 4; 2026-05-12: 4; 2026-05-13: 4; 2026-05-14: 4; 2026-05-15: 4; 2026-05-16: 4; 2026-05-18: 10; 2026-05-19: 10; 2026-05-20: 10; 2026-05-21: 10; 2026-05-22: 10; 2026-05-23: 10; 2026-05-25: 10; 2026-05-26: 10; 2026-05-27: 10; 2026-05-28: 10; 2026-05-29: 10; 2026-05-30: 10
[20 empty] | 0 |  |  | 0
4 | 0 | 0 | 4.0.0 | E2S Interior | [8 empty] | 522 |  |  |  |  | 2026-04-24 | 1.533% | 8 |  |  | 0
4 | 1 | 0 | 4.1.0 | FT15 Terminal Cable Canals (NTA) | [8 empty] | 24 | [5 empty] | 0% | 0 | 0% | 0% | 0
4 | 1 | 1 | 4.1.1 | New Design |  | MYA | [13 empty] | 0 |  |  | 0
4 | 1 | 2 | 4.1.2 | Approval by SOB / NTA Approval by URW |  | URW | [13 empty] | 0 |  |  | 0
4 | 1 | 3 | 4.1.3 | Procurement + Manufacturing |  | MYA |  | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  |  | 0% | 0 |  |  | 0
4 | 1 | 4 | 4.1.4 | Installation | 1.5 | MYA | C | 10 | 0 | 10 | 2 | 12 | 24 | 0 | 24 |  |  |  | 0% | 0 | 0% | 0% | 0
4 | 2 | 0 | 4.2.0 | WT-04 | [8 empty] | 96 | [5 empty] | 0% | 0 | 0% | 0% | 0
4 | 2 | 1 | 4.2.1 | Window Handle Installation + Adjustment | 1 | MYA | B | 214 | 0 | 214 | 2 | 24 | 48 | 48 | 0 | 2026-03-30 | 10 | 2026-04-10 | 0% | 0 | 0% | 0% | 0 |  | 2026-03-30: 4; 2026-03-31: 4; 2026-04-01: 4; 2026-04-02: 4; 2026-04-03: 4; 2026-04-04: 4; 2026-04-06: 4; 2026-04-07: 4; 2026-04-08: 4; 2026-04-09: 4; 2026-04-10: 4; 2026-04-11: 4
4 | 2 | 2 | 4.2.2 | Silicone/Gasket Control + Rectafication | 1 | MYA | A | 90 | 0 | 90 | 2 | 12 | 24 | 24 | 0 | 2026-04-09 | 5 | 2026-04-15 | 0% | 0 | 0% | 0% | 0 |  | 2026-04-09: 4; 2026-04-10: 4; 2026-04-11: 4; 2026-04-13: 4; 2026-04-14: 4; 2026-04-15: 4
4 | 2 | 3 | 4.2.3 | Interior Membrane Check + Touchup | 1 | MYA | A | 90 | 0 | 90 | 2 | 12 | 24 | 24 | 0 | 2026-04-16 | 5 | 2026-04-22 | 0% | 0 | 0% | 0% | 0 |  | 2026-04-16: 4; 2026-04-17: 4; 2026-04-18: 4; 2026-04-20: 4; 2026-04-21: 4; 2026-04-22: 4
4 | 3 | 0 | 4.3.0 | WT-1.5 | [8 empty] | 72 | [5 empty] | 0% | 0 | 0% | 0% | 0
4 | 3 | 1 | 4.3.1 | Window Handle Installation + Adjustment | 1 | MYA | B | 96 | 0 | 96 | 2 | 12 | 24 | 24 | 0 | 2026-04-13 | 10 | 2026-04-24 | 0% | 0 | 0% | 0% | 0 |  | 2026-04-13: 2; 2026-04-14: 2; 2026-04-15: 2; 2026-04-16: 2; 2026-04-17: 2; 2026-04-18: 2; 2026-04-20: 2; 2026-04-21: 2; 2026-04-22: 2; 2026-04-23: 2; 2026-04-24: 2; 2026-04-25: 2
4 | 3 | 2 | 4.3.2 | Silicone/Gasket Control + Rectafication | 1 | MYA | A | 78 | 0 | 78 | 2 | 12 | 24 | 24 | 0 | 2026-04-13 | 10 | 2026-04-24 | 0% | 0 | 0% | 0% | 0 |  | 2026-04-13: 2; 2026-04-14: 2; 2026-04-15: 2; 2026-04-16: 2; 2026-04-17: 2; 2026-04-18: 2; 2026-04-20: 2; 2026-04-21: 2; 2026-04-22: 2; 2026-04-23: 2; 2026-04-24: 2; 2026-04-25: 2
4 | 3 | 3 | 4.3.3 | Interior Membrane Check + Touchup | 1 | MYA | A | 78 | 0 | 78 | 2 | 12 | 24 | 24 | 0 | 2026-04-13 | 10 | 2026-04-24 | 0% | 0 | 0% | 0% | 0 |  | 2026-04-13: 2; 2026-04-14: 2; 2026-04-15: 2; 2026-04-16: 2; 2026-04-17: 2; 2026-04-18: 2; 2026-04-20: 2; 2026-04-21: 2; 2026-04-22: 2; 2026-04-23: 2; 2026-04-24: 2; 2026-04-25: 2
4 | 4 | 0 | 4.4.0 | FT-02 Zigzak | [8 empty] | 72 | [5 empty] | 0% | 0 | 0% | 0% | 0
4 | 4 | 1 | 4.4.1 | Window Handle Installation + Adjustment | 1 | MYA | B | 33 | 0 | 33 | 3 | 12 | 36 | 36 | 0 | 2026-04-13 | 5 | 2026-04-17 | 0% | 0 | 0% | 0% | 0 |  | 2026-04-13: 6; 2026-04-14: 6; 2026-04-15: 6; 2026-04-16: 6; 2026-04-17: 6; 2026-04-18: 6
4 | 4 | 2 | 4.4.2 | Silicone/Gasket Control + Rectafication | 1 | MYA | A | 255 | 0 | 255 | 2 | 6 | 12 | 12 | 0 | 2026-03-30 | 5 | 2026-04-03 | 0% | 0 | 0% | 0% | 0 |  | 2026-03-30: 2; 2026-03-31: 2; 2026-04-01: 2; 2026-04-02: 2; 2026-04-03: 2; 2026-04-04: 2
4 | 4 | 3 | 4.4.3 | Interior Membrane Check + Touchup | 1 | MYA | A | 79 | 0 | 79 | 2 | 12 | 24 | 24 | 0 | 2026-03-30 | 10 | 2026-04-10 | 0% | 0 | 0% | 0% | 0 |  | 2026-03-30: 2; 2026-03-31: 2; 2026-04-01: 2; 2026-04-02: 2; 2026-04-03: 2; 2026-04-04: 2; 2026-04-06: 2; 2026-04-07: 2; 2026-04-08: 2; 2026-04-09: 2; 2026-04-10: 2; 2026-04-11: 2
4 | 5 | 0 | 4.5.0 | FT-14 | [8 empty] | 24 | [5 empty] | 0% | 0 | 0% | 0% | 0
4 | 5 | 1 | 4.5.1 | Aluminum sheet installation | 1 | MYA | B | 43 | 0 | 43 | 2 | 6 | 12 | 12 | 0 | 2026-04-20 | 5 | 2026-04-24 | 0% | 0 | 0% | 0% | 0 |  | 2026-04-20: 2; 2026-04-21: 2; 2026-04-22: 2; 2026-04-23: 2; 2026-04-24: 2; 2026-04-25: 2
4 | 5 | 2 | 4.5.2 | Window Handle Installation + Adjustment | 1 | MYA | B | 43 | 0 | 43 | 2 | 6 | 12 | 12 | 0 | 2026-04-20 | 5 | 2026-04-24 | 0% | 0 | 0% | 0% | 0 |  | 2026-04-20: 2; 2026-04-21: 2; 2026-04-22: 2; 2026-04-23: 2; 2026-04-24: 2; 2026-04-25: 2
4 | 6 | 0 | 4.6.0 | FT-05 | [8 empty] | 24 | [5 empty] | 0% | 0 | 0% | 0% | 0
4 | 6 | 1 | 4.6.1 | Membrane Control + Rectafication | 1 | MYA | A | 18 | 0 | 18 | 2 | 12 | 24 | 24 | 0 | 2026-04-13 | 10 | 2026-04-24 | 0% | 0 | 0% | 0% | 0 |  | 2026-04-13: 2; 2026-04-14: 2; 2026-04-15: 2; 2026-04-16: 2; 2026-04-17: 2; 2026-04-18: 2; 2026-04-20: 2; 2026-04-21: 2; 2026-04-22: 2; 2026-04-23: 2; 2026-04-24: 2; 2026-04-25: 2
4 | 7 | 0 | 4.7.0 | FT-03 | [8 empty] | 84 | [5 empty] | 0% | 0 | 0% | 0% | 0
4 | 7 | 1 | 4.7.1 | Aluminum sheet installation | 1 | MYA | B | 107 | 0 | 107 | 2 | 12 | 24 | 24 | 0 | 2026-04-13 | 10 | 2026-04-24 | 0% | 0 | 0% | 0% | 0 |  | 2026-04-13: 2; 2026-04-14: 2; 2026-04-15: 2; 2026-04-16: 2; 2026-04-17: 2; 2026-04-18: 2; 2026-04-20: 2; 2026-04-21: 2; 2026-04-22: 2; 2026-04-23: 2; 2026-04-24: 2; 2026-04-25: 2
4 | 7 | 2 | 4.7.2 | Window Handle Installation + Adjustment | 1 | MYA | B | 16 | 0 | 16 | 2 | 6 | 12 | 12 | 0 | 2026-04-20 | 5 | 2026-04-24 | 0% | 0 | 0% | 0% | 0 |  | 2026-04-20: 2; 2026-04-21: 2; 2026-04-22: 2; 2026-04-23: 2; 2026-04-24: 2; 2026-04-25: 2
4 | 7 | 3 | 4.7.3 | Paint - Touch up | 1 | MYA | A | 107 | 0 | 107 | 2 | 24 | 48 | 48 | 0 | 2026-03-30 | 20 | 2026-04-24 | 0% | 0 | 0% | 0% | 0 |  | 2026-03-30: 2; 2026-03-31: 2; 2026-04-01: 2; 2026-04-02: 2; 2026-04-03: 2; 2026-04-04: 2; 2026-04-06: 2; 2026-04-07: 2; 2026-04-08: 2; 2026-04-09: 2; 2026-04-10: 2; 2026-04-11: 2; 2026-04-13: 2; 2026-04-14: 2; 2026-04-15: 2; 2026-04-16: 2; 2026-04-17: 2; 2026-04-18: 2; 2026-04-20: 2; 2026-04-21: 2; 2026-04-22: 2; 2026-04-23: 2; 2026-04-24: 2; 2026-04-25: 2
4 | 8 | 0 | 4.8.0 | WT-1.6 | [8 empty] | 8 | [5 empty] | 0% | 0 | 0% | 0% | 0
4 | 8 | 1 | 4.8.1 | Membrane Control + Rectafication | 1 | MYA | A | 2 | 0 | 2 | 2 | 4 | 8 | 8 | 0 | 2026-04-06 | 4 | 2026-04-09 | 0% | 0 | 0% | 0% | 0 |  | 2026-04-06: 2; 2026-04-07: 2; 2026-04-08: 2; 2026-04-09: 2
4 | 9 | 0 | 4.9.0 | FT-06 Pool facade | [8 empty] | 76 | [5 empty] | 5.263% | 4 | 0% | 0% | 0
4 | 9 | 1 | 4.9.1 | Mock-up on Site | 1.5 | MYA |  | 1 | 1 | 0 | 2 | 2 | 4 | 4 | 0 | 2025-11-26 | 2 | 2025-11-27 | 100% | 4 | 0% | 100% | 4 |  | 2025-11-26: 2; 2025-11-27: 2
4 | 9 | 2 | 4.9.2 | Approval by SOB/DSI/URW |  | URW | [13 empty] | 0 |  |  | 0
4 | 9 | 3 | 4.9.3 | Procurement + Manufacturing |  | MYA |  | 18 | 0 | 18 | [8 empty] | 0% | 0 |  |  | 0
4 | 9 | 4 | 4.9.4 | Installation | 1.5 | MYA | A | 18 | 0 | 18 | 4 | 18 | 72 | 72 | 0 | 2026-04-06 | 11 | 2026-04-20 | 0% | 0 | 0% | 0% | 0 |  | 2026-04-06: 2; 2026-04-07: 2; 2026-04-08: 2; 2026-04-09: 2; 2026-04-10: 2; 2026-04-11: 2; 2026-04-13: 2; 2026-04-14: 2; 2026-04-15: 2; 2026-04-16: 2; 2026-04-17: 2; 2026-04-18: 2; 2026-04-20: 6; 2026-04-21: 6; 2026-04-22: 6; 2026-04-23: 10; 2026-04-24: 10; 2026-04-25: 10
4 | 10 | 0 | 4.10.0 | FT03 Acoustic Reinforcement | [8 empty] | 42 | [5 empty] | 9.524% | 4 | 0% | 0% | 0
4 | 10 | 1 | 4.10.1 | Mock-up on Site | 1.5 | MYA |  | 1 | 1 | 0 | 2 | 2 | 4 | 4 | 0 | 2025-11-28 | 1 | 2025-11-28 | 100% | 4 | 0% | 100% | 4 |  | 2025-11-28: 2; 2025-11-29: 2
4 | 10 | 2 | 4.10.2 | Acoustic Testing |  | MYA |  | 1 | 0 | 1 | 2 | 1 | 2 | 0 | 2 |  |  |  | 0% | 0 | 0% | 0% | 0
4 | 10 | 3 | 4.10.3 | Approval by SOB/DSI/URW |  | URW | [13 empty] | 0 |  |  | 0
4 | 10 | 4 | 4.10.4 | Procurement + Manufacturing |  | MYA |  | 20 | 0 | 20 |  |  |  | 0 | 0 |  |  |  | 0% | 0 |  |  | 0
4 | 10 | 5 | 4.10.5 | Installation | 1.5 | MYA | A | 20 | 0 | 20 | 2 | 18 | 36 | 36 | 0 | 2026-04-27 | 5 | 2026-05-01 | 0% | 0 | 0% | 0% | 0 |  | 2026-04-27: 6; 2026-04-28: 6; 2026-04-29: 6; 2026-04-30: 6; 2026-05-01: 6; 2026-05-02: 6
4 | 11 | 0 | 4.11.0 | Documentation + Testing
4 | 11 | 1 | 4.11.1 | WT04 |  | MYA
4 | 11 | 2 | 4.11.2 | WT01.5 |  | MYA
4 | 11 | 3 | 4.11.3 | FT15 |  | MYA
4 | 11 | 4 | 4.11.4 | FT03 |  | MYA
4 | 11 | 5 | 4.11.5 | FT06 |  | MYA
4 | 11 | 6 | 4.11.6 | FT09 |  | MYA
4 | 11 | 7 | 4.11.7 | FT14 |  | MYA
4 | 12 | 0 | 4.12.0 | Warehouse + Supervisor | [20 empty] | 2025-11-24: 3; 2025-11-25: 3; 2025-11-26: 3; 2025-11-27: 3; 2025-11-28: 3; 2025-11-29: 3; 2025-12-01: 2; 2025-12-02: 2; 2025-12-03: 2; 2025-12-04: 2; 2025-12-05: 2; 2025-12-06: 2; 2025-12-08: 2; 2025-12-09: 2; 2025-12-10: 2; 2025-12-11: 2; 2025-12-12: 2; 2025-12-13: 2; 2025-12-15: 2; 2025-12-16: 2; 2025-12-17: 2; 2025-12-18: 2; 2025-12-19: 2; 2025-12-20: 2; 2025-12-22: 2; 2025-12-23: 2; 2025-12-24: 2; 2025-12-25: 2; 2025-12-26: 2; 2025-12-27: 2; 2025-12-29: 2; 2025-12-30: 2; 2025-12-31: 2; 2026-01-01: 2; 2026-01-02: 2; 2026-01-03: 2; 2026-01-05: 2; 2026-01-06: 2; 2026-01-07: 2; 2026-01-08: 2; 2026-01-09: 2; 2026-01-10: 2; 2026-01-12: 2; 2026-01-13: 2; 2026-01-14: 2; 2026-01-15: 2; 2026-01-16: 2; 2026-01-17: 2; 2026-01-19: 2; 2026-01-20: 2; 2026-01-21: 2; 2026-01-22: 2; 2026-01-23: 2; 2026-01-24: 2; 2026-01-26: 2; 2026-01-27: 2; 2026-01-28: 2; 2026-01-29: 2; 2026-01-30: 2; 2026-01-31: 2; 2026-02-02: 2; 2026-02-03: 2; 2026-02-04: 2; 2026-02-05: 2; 2026-02-06: 2; 2026-02-07: 2; 2026-02-09: 2; 2026-02-10: 2; 2026-02-11: 2; 2026-02-12: 2; 2026-02-13: 2; 2026-02-14: 2; 2026-02-16: 2; 2026-02-17: 2; 2026-02-18: 2; 2026-02-19: 2; 2026-02-20: 2; 2026-02-21: 2; 2026-02-23: 2; 2026-02-24: 2; 2026-02-25: 2; 2026-02-26: 2; 2026-02-27: 2; 2026-02-28: 2; 2026-03-02: 2; 2026-03-03: 2; 2026-03-04: 2; 2026-03-05: 2; 2026-03-06: 2; 2026-03-07: 2; 2026-03-09: 2; 2026-03-10: 2; 2026-03-11: 2; 2026-03-12: 2; 2026-03-13: 2; 2026-03-14: 2; 2026-03-16: 2; 2026-03-17: 2; 2026-03-18: 2; 2026-03-19: 2; 2026-03-20: 2; 2026-03-21: 2; 2026-03-23: 2; 2026-03-24: 2; 2026-03-25: 2; 2026-03-26: 2; 2026-03-27: 2; 2026-03-28: 2; 2026-03-30: 2; 2026-03-31: 2; 2026-04-01: 2; 2026-04-02: 2; 2026-04-03: 2; 2026-04-04: 2; 2026-04-06: 2; 2026-04-07: 2; 2026-04-08: 2; 2026-04-09: 2; 2026-04-10: 2; 2026-04-11: 2; 2026-04-13: 2; 2026-04-14: 2; 2026-04-15: 2; 2026-04-16: 2; 2026-04-17: 2; 2026-04-18: 2; 2026-04-20: 2; 2026-04-21: 2; 2026-04-22: 2; 2026-04-23: 2; 2026-04-24: 2; 2026-04-25: 2; 2026-04-27: 2; 2026-04-28: 2; 2026-04-29: 2; 2026-04-30: 2; 2026-05-01: 2; 2026-05-02: 2; 2026-05-04: 2; 2026-05-05: 2; 2026-05-06: 2; 2026-05-07: 2; 2026-05-08: 2; 2026-05-09: 2; 2026-05-11: 2; 2026-05-12: 2; 2026-05-13: 2; 2026-05-14: 2; 2026-05-15: 2; 2026-05-16: 2; 2026-05-18: 2; 2026-05-19: 2; 2026-05-20: 2; 2026-05-21: 2; 2026-05-22: 2; 2026-05-23: 2; 2026-05-25: 2; 2026-05-26: 2; 2026-05-27: 2; 2026-05-28: 2; 2026-05-29: 2; 2026-05-30: 2

## Prerequisites
Prerequisites
1 | Interior Access (Inc. Electricity + HSE Conditions)
2 | Exterior Access
3 | Exterior Manlift Access
4 | Tower Crane Lifting
5 | Scafolding Build-Up Allowance
6 | Massive Scafolding
7 | Scafolding Removal
8 | Tower Crane Material Transport to Innenhof
9
10
11
12
13
14
15
16
17
18
19
20