## E2NS_WBS
WESTFIELD HAMBURG — E2NS PACKAGE — WORK BREAKDOWN STRUCTURE
Contract: PRODE000200773 ¦ Metal Yapı GmbH ¦ Rev. 003 — Feb 2025
WBS | Description | Building | NTA Ref. | Status | Budget (€) | Payment Agreed (€) | Target KW | Notes
1.0 | Already Executed — Progress since April 2024 | E2NS |  | DONE | 382722.57 |  | KW03
1.1 | E2N — Remaining Contract Works | E2N
1.1.1 | FT07/FT08/FT11/FT15 East Façade | E2N |  |  | 14255.01 |  | KW11 | Punch window types, remaining installation ¦ Parent group: 4 sub-levels
1.1.1.1 | FT07 Punch Window East Facade | E2N | [5 empty] | FT07 punch windows
1.1.1.2 | FT08 Punch Window East Facade | E2N | [5 empty] | FT08 punch windows
1.1.1.3 | FT11 East Facade | E2N | [5 empty] | FT11 scope
1.1.1.4 | FT15 East Remaining Installation | E2N | [5 empty] | FT15 East panels
1.1.2 | FT15: E2N (NW) / E2S (ESW) + Terminal Cable Canals | E2N | NTA060 |  | 51428.01 |  | KW09 | Incl. NTA060 Terminal Cable Canals ¦ Parent group: 6 sub-levels
1.1.2.1 | FT15 E2N North | E2N | [5 empty] | FT15 North facade
1.1.2.2 | FT15 E2N West | E2N | [5 empty] | FT15 West facade
1.1.2.3 | FT15 E2S East | E2S | [5 empty] | FT15 E2S East facade
1.1.2.4 | FT15 E2S South | E2S | [5 empty] | FT15 E2S South facade
1.1.2.5 | FT15 E2S West | E2S | [5 empty] | FT15 E2S West facade
1.1.2.6 | Terminal Cable Canals | E2S | NTA060 |  |  |  |  | NTA060 Terminal cable canals
1.1.3 | Lochfenster E2N & E2S | E2N |  |  | 22479.63 |  | KW21 | Combined punch window scope ¦ Parent group: 2 sub-levels
1.1.3.1 | Lochfenster E2N | E2N | [5 empty] | Punch windows E2N
1.1.3.2 | Lochfenster E2S | E2S | [5 empty] | Punch windows E2S
1.1.4 | Türen E2N | E2N |  |  | 25685.49 |  | KW23 | Door installation & commissioning
1.1.5 | Main Entrance Canopy — E2N Novotel | E2N |  |  | 1306.13 |  | KW21 | Canopy completion
1.1.6 | Lamellenfassade FT18 — E2N | E2N |  |  | 11045.64 |  | KW15 | Louvre façade completion
1.1.7 | Stabgeländer (Balustrades) | E2NS |  |  | 21663.4 |  |  | Split from combined item — LV 01.08/02.08 + NTA053
1.1.7.1 | Stabgeländer E2S — Glas-/Stabgeländer RT01/RT02 | E2S |  |  |  |  | KW21 | LV 02.08 Glas-/Stabgeländer
1.1.7.2 | Stabgeländer E2N — Edelstahl-Stabgeländer RT02 | E2N |  |  |  |  | KW21 | LV 01.08 Edelstahl-Stabgeländer
1.1.7.3 | Additional Steel Balustrade | E2N | NTA053 |  | 15370 |  | KW21 | Re-manufactured 2 pcs at E2N 3.OG
1.1.8 | Attikaabdeckungen E2N & E2S | E2NS |  |  | 14593.6 |  | KW21 | Parent group: 2 sub-levels
1.1.8.1 | Attikaabdeckungen E2N | E2N | [5 empty] | Parapet capping E2N
1.1.8.2 | Attikaabdeckungen E2S | E2S | [5 empty] | Parapet capping E2S
1.1.9 | Acoustic Panel System — E2N Roof (FT18) | E2N | [5 empty] | Parent group: 3 sub-levels
1.1.9.1 | Acoustic Panel — Material/MOS | E2N | NTA046 |  | 95000 |  | KW09 | 450 m² + 13 T — Acoustic Roof panels
1.1.9.2 | Acoustic Panels — Subframe/MOS | E2N | NTA046 |  | 114000 |  | KW11 | Substructure for acoustic panels
1.1.9.3 | Acoustic Panels — Installation + Cat Walk | E2N | NTA046/047 |  | 151496.06 |  | KW15 | Installation incl. NTA047 Cat Walk grilles
1.1.10 | Final Façade Cleaning — E2N | E2N |  |  |  |  | KW23 | Split from combined cleaning item
1.1.11 | Final Façade Cleaning — E2S | E2S |  |  |  |  | KW23 | Split from combined cleaning item
1.2 | E2S — Remaining Contract Works | E2S
1.2.1 | PR-Fassade — FT02/FT03/FT10/FT14 | E2S |  |  | 35683.84 |  | KW21 | Parent group: 4 sub-levels
1.2.1.1 | PR-Fassade FT02 | E2S | [5 empty] | FT02 curtain wall
1.2.1.2 | PR-Fassade FT03 | E2S | [5 empty] | FT03 curtain wall
1.2.1.3 | PR-Fassade FT10 | E2S | [5 empty] | FT10 curtain wall
1.2.1.4 | PR-Fassade FT14 | E2S | [5 empty] | FT14 curtain wall
1.2.2 | PR-Fassade — FT05/FT06/FT09 + Interkom Glass | E2S | NTA063 |  | 55655.92 |  | KW15 | Incl. NTA063 Interkom Glasses ¦ Parent group: 4 sub-levels
1.2.2.1 | PR-Fassade FT05 | E2S | [5 empty] | FT05 curtain wall
1.2.2.2 | PR-Fassade FT06 | E2S | [5 empty] | FT06 curtain wall
1.2.2.3 | PR-Fassade FT09 | E2S | [5 empty] | FT09 curtain wall
1.2.2.4 | Interkom Glass | E2S | NTA063 |  |  |  |  | NTA063 Interkom glasses
1.2.3 | Lochfenster — WT04 | E2S |  |  | 47907.39 |  | KW13
1.2.4 | Lochfenster — WT01.5 / WT01.6 / WT01.7 | E2S |  |  | 33140.47 |  | KW15 | Parent group: 3 sub-levels
1.2.4.1 | Lochfenster WT01.5 | E2S | [5 empty] | WT01.5 punch windows
1.2.4.2 | Lochfenster WT01.6 | E2S | [5 empty] | WT01.6 punch windows
1.2.4.3 | Lochfenster WT01.7 | E2S | [5 empty] | WT01.7 punch windows
1.2.5 | Türen E2S | E2S |  |  | 22620.58 |  | KW21
1.2.6 | Lamellenfassade FT18 — E2S | E2S |  |  | 20452.57 |  | KW19
1.2.7 | Main Entrance Canopy — E2S Pullman | E2S |  |  | 30526.51 |  | KW19
1.2.8 | Alu Cladding Shafts — FT16 | E2S |  |  | 57000 |  | KW17
1.2.9 | Aluminium Soffit — FT17 | E2S |  |  | 70643.57 |  | KW21
1.3 | E2N — Additional Works (Nachträge) | E2N
1.3.1 | Bottom Sheet WT01 Reinforcement | E2N | NTA050 |  | 35557 |  | KW11 | ~80 pcs, modification on WT01 windows
1.3.2 | Cutting Bottom Sheet 3.OG North | E2N | NTA051 |  | 16450.5 |  | KW11 | ~15 pcs, 3.OG North façade
1.3.3 | 1141 Partial Additional Attika | E2N | NTA052 |  | 11876.5 |  |  | 4 mt. inclined Al. Sheet 7.OG West
1.3.4 | Attika Removal + Substructure East | E2N | NTA048 | DONE | 15875 |  |  | 3 axes dismantled for electrical
1.3.5 | E2N Courtyard Water Tap | E2N | NTA065 |  | 16955.14 |  |  | Glass replacement
1.4 | E2S — Additional Works (Nachträge) | E2S
1.4.1 | Justification Package — NTA 048/049/054/055/056/057/062 | E2S |  | DONE | 161453.55 |  |  | Each NTA listed individually below
1.4.1.1 | Attika Removal + Substructure East | E2N | NTA048 | DONE | 15875 |  | KW05 | 3 axes — already executed
1.4.1.2 | Steel Construction for Masonry E2S West | E2S | NTA049 | DONE | 22301 |  | KW05 | 2 psch additional steel
1.4.1.3 | 3.OG Attika Rectification | E2S | NTA054 |  | 31624.8 |  | KW07 | ~60 pcs revised roofing drawings
1.4.1.4 | 3.OG Balustrade + Machinery | E2S | NTA055 |  | 11320 |  |  | Temporary balustrades 3rd floor
1.4.1.5 | FT18 Late + Tough Installation | E2S | NTA056 |  | 159720 |  |  | ~140 pcs, roofing delay + crane
1.4.1.6 | Design Revision Glass Balustrade | E2S | NTA057 |  | 22240 |  |  | LPH5 design revision concrete connection
1.4.1.7 | FT12 Canopy Drainage Pipe | E2S | NTA062 |  | 5834 |  |  | Special drainage specification
1.4.2 | 3.OG Attika Rectification (Execution) | E2S | NTA054 |  | 21377.79 |  | KW07
1.4.3 | NTA058 (FT14 Spandrel) + NTA059 (E2S West Louvers) | E2S | NTA058/059 |  | 78344.18 |  | KW17 | 4 sub-groups as requested
1.4.3.1 | FT14 Additional Spandrel Panel — Design & Procurement | E2S | NTA058 |  | 18807.88 |  |  | 7 pcs, vision glass → spandrel
1.4.3.2 | FT14 Additional Spandrel Panel — Installation | E2S | NTA058 |  |  |  |  | Site execution
1.4.3.3 | E2S West Vent behind Louvers — Design & Material | E2S | NTA059 |  | 41189.26 |  |  | 2 pcs, additional vent requested by SOB
1.4.3.4 | E2S West Vent behind Louvers — Installation | E2S | NTA059 |  |  |  |  | Site execution
1.4.4 | FT16 Additional Steel Structure | E2S | NTA061 |  | 215036 | 195908.55 | KW19 | ~15 T steel, not in original MYA scope
1.5 | Final Milestone — E2NS | E2NS |  |  | 73603.72 |  | KW23 | Due on completion of all final snags & submission of all documents

## D1D2_WBS
WESTFIELD HAMBURG — D1D2 PACKAGE — WORK BREAKDOWN STRUCTURE
Contract: PRODE000200672 ¦ Metal Yapı GmbH ¦ Rev. 003 — Feb 2025
WBS | Description | Building | NTA Ref. | Status | Budget (€) | Payment Agreed (€) | Target KW | Notes
2.1 | D1D2 — Remaining Contract Works / Defect Rectification | D1+D2
2.1.1 | Interior Façade Defects Removal — D2 (12 Floors) | D2 |  |  | 95000 |  |  | MERGED: prev. 01.11 + 01.12 (2×6 Floors → 12 Floors) ¦ Parent group: 2 sub-levels
2.1.1.1 | Interior Facade Defects D2 Floors 1-6 | D2 | [5 empty] | D2 lower floors
2.1.1.2 | Interior Facade Defects D2 Floors 7-12 | D2 | [5 empty] | D2 upper floors
2.1.2 | Interior Façade Defects Removal — D1 (12 Floors) | D1 |  |  | 95000 |  |  | MERGED: prev. 01.13 + 01.14 (2×6 Floors → 12 Floors) ¦ Parent group: 2 sub-levels
2.1.2.1 | Interior Facade Defects D1 Floors 1-6 | D1 | [5 empty] | D1 lower floors
2.1.2.2 | Interior Facade Defects D1 Floors 7-12 | D1 | [5 empty] | D1 upper floors
2.1.3 | Exterior Façade Defects Removal | D1+D2 |  |  | 84550 |  | KW17 | Parent group: 2 sub-levels
2.1.3.1 | Exterior Facade Defects D1 | D1 | [5 empty] | D1 exterior defects
2.1.3.2 | Exterior Facade Defects D2 | D2 | [5 empty] | D2 exterior defects
2.1.4 | Glass Replacement | D1+D2 |  |  | 79325 |  | KW17 | Parent group: 2 sub-levels
2.1.4.1 | Glass Replacement D1 | D1 | [5 empty] | D1 glass replacement
2.1.4.2 | Glass Replacement D2 | D2 | [5 empty] | D2 glass replacement
2.1.5 | Staircases (incl. NTA040 Staircase Design Revision) | D2 | NTA040 |  | 133000 |  |  | MERGED: prev. 01.17+01.18, 2 sub-groups
2.1.5.1 | Staircases — Material on Site | D2 | NTA040 |  | 85500 |  | KW09 | Materials delivered + NTA040 design revision
2.1.5.2 | Staircases — Completion & Installation | D2 | NTA040 |  | 47500 |  | KW13 | Full completion of staircase installation
2.1.6 | Doors Defects | D1+D2 |  |  | 65075 |  | KW21 | Parent group: 2 sub-levels
2.1.6.1 | Doors Defects D1 | D1 | [5 empty] | D1 door defects
2.1.6.2 | Doors Defects D2 | D2 | [5 empty] | D2 door defects
2.1.7 | Electrical Bird Deterrence System — D2 (12 Floors) | D2 |  |  | 101149.83 |  | KW13 | Parent group: 2 sub-levels
2.1.7.1 | Bird Deterrence D2 Floors 1-6 | D2 | [5 empty] | D2 lower floors
2.1.7.2 | Bird Deterrence D2 Floors 7-12 | D2 | [5 empty] | D2 upper floors
2.1.8 | Electrical Bird Deterrence System — D1 (12 Floors) | D1 |  |  | 101149.83 |  | KW07 | Parent group: 2 sub-levels
2.1.8.1 | Bird Deterrence D1 Floors 1-6 | D1 | [5 empty] | D1 lower floors
2.1.8.2 | Bird Deterrence D1 Floors 7-12 | D1 | [5 empty] | D1 upper floors
2.1.9 | Final Façade Cleaning — D1+D2 | D1+D2 |  |  | 47500 |  | KW17 | Parent group: 2 sub-levels
2.1.9.1 | Final Facade Cleaning D1 | D1 | [5 empty] | D1 final cleaning
2.1.9.2 | Final Facade Cleaning D2 | D2 | [5 empty] | D2 final cleaning
2.2 | D1D2 — Additional Works (Nachträge) | D1+D2
2.2.1 | Staircase Design Revision | D2 | NTA040 |  | 144952 | 20273.95 | KW05 | Design revision due to roofing/fireproofing changes
2.2.2 | 4.OG Additional Vent — MOS (Material) | D2 | NTA041 |  | 25420 | 14535 | KW07
2.2.3 | 4.OG Additional Vent — Installation | D2 | NTA041 |  |  | 5700 | KW11
2.2.4 | Justification Package — NTA 042/043/044/045/D046 | D1+D2 |  | DONE | 52622 | 33750.65 | KW05 | Each NTA listed individually below
2.2.4.1 | 1.OG Perforated Sheets | D2 | NTA042 | DONE | 15722 |  |  | 10 m² requested by TGA
2.2.4.2 | Additional Gal. Sheet on Roof | D2 | NTA043 | DONE | 8007 |  |  | 16 pcs, D2.5/D2.14/D1.14
2.2.4.3 | Boon Edam Commissioning | D2 | NTA044 | DONE | 1599 |  |  | New location for revolving door
2.2.4.4 | Pesca Water Ingress × 4 Times | D1 | NTA045 | DONE | 19339 |  |  | D1 Pesca area investigation
2.2.4.5 | Logo Anchorage Installation with Abseilers | D2 | DNTA046 |  | 7955 | 5794.05 | KW07 | Logo anchorage priced on abseil basis
2.2.5 | Additional Limitator on Windows | D1+D2 | NTA039 |  |  |  |  | ~250 pcs, requested by DSI — no agreed price yet
2.3 | Final Milestone — D1D2 | D1+D2 |  |  | 46410.7 |  | KW23 | Due on completion of all final snags & submission of all documents

## NTA_Xref
NTA CROSS-REFERENCE — Claim List ↔ Payment Agreement ↔ WBS
NTA No. | Package | Title | Building | Claim Budget (€) | Payment Agreed (€) | WBS Ref. | Payment Ref. | Status
NTA046 | E2NS | Acoustic Roof (FT18) | E2N | 691264 |  | 1.1.9 | 02.19–02.21 | In Progress
NTA047 | E2NS | Cat Walk on Acoustic Roof | E2N | 19363 |  | 1.1.9.3 | 02.21 | In Progress
NTA048 | E2NS | Attika Removal + Substructure East | E2N | 15875 |  | 1.4.1.1 | 05.11 | DONE
NTA049 | E2NS | Steel Construction for Masonry E2S West | E2S | 22301 |  | 1.4.1.2 | 05.11 | DONE
NTA050 | E2NS | Bottom Sheet WT01 Reinforcement | E2N | 35557 |  | 1.3.1 | 03.11
NTA051 | E2NS | Cutting Bottom Sheet 3.OG North | E2N | 16450.5 |  | 1.3.2 | 03.11
NTA052 | E2NS | 1141 Partial Additional Attika | E2N | 11876.5 |  | 1.3.3 | —
NTA053 | E2NS | Additional Steel Balustrade | E2N | 15370 |  | 1.1.7.3 | 02.17
NTA054 | E2NS | 3.OG Attika Rectification | E2S | 31624.8 |  | 1.4.1.3 / 1.4.2 | 05.11 / 05.12
NTA055 | E2NS | 3.OG Balustrade + Machinery | E2S | 11320 |  | 1.4.1.4 | 05.11
NTA056 | E2NS | FT18 Late + Tough Installation | E2S | 159720 |  | 1.4.1.5 | 05.11
NTA057 | E2NS | Design Revision Glass Balustrade | E2S | 22240 |  | 1.4.1.6 | 05.11
NTA058 | E2NS | FT14 Additional Spandrel Panel | E2S | 18807.88 |  | 1.4.3.1–.2 | 05.13
NTA059 | E2NS | E2S West Vent behind Louvers | E2S | 41189.26 |  | 1.4.3.3–.4 | 05.13
NTA060 | E2NS | Terminal Cable Canals | E2S | 20170 |  | 1.1.2 | 02.12
NTA061 | E2NS | FT16 Additional Steel Structure | E2S | 215036 | 195908.55 | 1.4.4 | 05.14
NTA062 | E2NS | FT12 Canopy Drainage Pipe | E2S | 5834 |  | 1.4.1.7 | 05.11
NTA063 | E2NS | Interkom Glasses | E2S | 51058.39 |  | 1.2.2 | 04.12
NTA065 | E2NS | E2N Courtyard Water Tap | E2N | 16955.14 |  | 1.3.5 | —
NTA039 | D1D2 | Additional Limitator on Windows | D1+D2 |  |  | 2.2.5 | — | No price
NTA040 | D1D2 | Staircase Design Revision | D2 | 144952 | 20273.95 | 2.2.1 / 2.1.5 | 02.11
NTA041 | D1D2 | 4.OG Additional Vent | D2 | 25420 | 20235 | 2.2.2 / 2.2.3 | 02.12/02.13
NTA042 | D1D2 | 1.OG Perforated Sheets | D2 | 15722 |  | 2.2.4.1 | 02.14 | DONE
NTA043 | D1D2 | Additional Gal. Sheet on Roof | D2 | 8007 |  | 2.2.4.2 | 02.14 | DONE
NTA044 | D1D2 | Boon Edam Commissioning | D2 | 1599 |  | 2.2.4.3 | 02.14 | DONE
NTA045 | D1D2 | Pesca Water Ingress × 4 | D1 | 19339 |  | 2.2.4.4 | 02.14 | DONE
DNTA046 | D1D2 | Logo Anchorage with Abseilers | D2 | 7955 | 5794.05 | 2.2.4.5 | 02.15

## Change_Log
WBS Restructuring — Change Log
# | Section | Change Description | Package
1 | 1.1.7 → 1.1.7.1/.2/.3 | Stabgeländer split: E2S / E2N / NTA053 — 3 sub-items | E2NS
2 | 1.1.9 → 1.1.9.1/.2/.3 | Acoustic Panel grouped: Material / Subframe / Installation+CatWalk as sub-levels | E2NS
3 | 1.1.10 + 1.1.11 | Final Façade Cleaning split into E2N and E2S | E2NS
4 | 1.4.1 → 7 sub-items | Each NTA in justification package listed as individual sub-group | E2NS
5 | 1.4.3 → 4 sub-items | NTA058+059 split into 4 sub-groups (Design+Install per NTA) | E2NS
6 | 2.1.1+2.1.2 merged | Interior Defects D2: 2×6 Floors → 1×12 Floors | D1D2
7 | 2.1.3+2.1.4 merged | Interior Defects D1: 2×6 Floors → 1×12 Floors | D1D2
8 | 2.1.5 → 2.1.5.1/.2 | Staircases merged under parent with 2 sub-groups (Material + Completion) | D1D2
9 | 2.2.4 → 5 sub-items | Each NTA in justification package listed as individual sub-group | D1D2
10 | NTA039 added | Additional Limitator (~250 pcs) — no agreed price, tracked in WBS | D1D2
11 | 1.1.1 -> 4 sub-items | FT07/FT08/FT11/FT15 East split into 4 facade types | E2NS
12 | 1.1.2 -> 6 sub-items | FT15 E2N N/W + E2S E/S/W + NTA060 Terminal Cable Canals | E2NS
13 | 1.1.3 -> 2 sub-items | Lochfenster split: E2N / E2S | E2NS
14 | 1.1.8 -> 2 sub-items | Attikaabdeckungen split: E2N / E2S | E2NS
15 | 1.2.1 -> 4 sub-items | PR-Fassade FT02/FT03/FT10/FT14 each as sub-item | E2NS
16 | 1.2.2 -> 4 sub-items | PR-Fassade FT05/FT06/FT09 + NTA063 Interkom as sub-items | E2NS
17 | 1.2.4 -> 3 sub-items | Lochfenster WT01.5/WT01.6/WT01.7 each as sub-item | E2NS
18 | 2.1.1 -> 2 sub-items | Interior Defects D2: Floors 1-6 / Floors 7-12 | D1D2
19 | 2.1.2 -> 2 sub-items | Interior Defects D1: Floors 1-6 / Floors 7-12 | D1D2
20 | 2.1.3 -> 2 sub-items | Exterior Defects split: D1 / D2 | D1D2
21 | 2.1.4 -> 2 sub-items | Glass Replacement split: D1 / D2 | D1D2
22 | 2.1.6 -> 2 sub-items | Doors Defects split: D1 / D2 | D1D2
23 | 2.1.7 -> 2 sub-items | Bird Deterrence D2: Floors 1-6 / Floors 7-12 | D1D2
24 | 2.1.8 -> 2 sub-items | Bird Deterrence D1: Floors 1-6 / Floors 7-12 | D1D2
25 | 2.1.9 -> 2 sub-items | Final Cleaning split: D1 / D2 | D1D2